## Changes
Module | Description | Status
Create Project | Oracle Project ID is mandatory. Right handside menu will be enabled only when Oracle ID is added. Bring it under new project and make it mandatory. | Closed
Project Reporting | AI Processing to be enabled. If AI data is available for the screen, then AI button will be enabled | Pending - Last
Maintain Project | Project Type - Consulting to be added, | Closed
Maintain Project | Introduce Region field | Closed
Maintain Project | Remove Billing Type. | Closed
Maintain Project | Add Critical Flag (Yes,N0o), Add Product Flag (Yes/No). If Product is Yes, Product Combo should be added. | Closed
Maintain Project | Add Geo Head field in Delivery Team section. it should be defaulted. | Closed
Maintain Project | In Send for Approval, All the fields in Project Profile are mandatory. That should be validated | Closed
Maintain Project | Add Consulting type and measurement Effort Variation, Schedule Performance Index, Cost Performance Index | Closed
Maintain Project | Baseline and Formula to be added in measurement section (QA to provide) | Closed
Maintain Project | Remove Engagement Type. | Closed
Amend Project | After Approval All the fields can be changes except Project Type | Closed
Maintain Project | Milestone should be renamed as Payment Milestone | Closed
Maintain Project | RAIDO is non mandatory for Approval. Move RAIDO to a separate section (Project Register) | Closed
DE Flow | DE role to be developed. Approval should come to DE | Closed
Project Reporting | DE to be removed from PM project charter. | Closed
DE Flow | PM -> Sent To Approval DE -> Approve / Reject | Closed
Main App | Create Project, Report Project, Amend Project | Closed
Project Reporting | Remove Project Charter from Project Reporting (Weekly Reporting) | Closed
Maintain Project | In Project Creation, Add Resource Allocated (Data will be pulled from Oracle on daily) under project Charter. In Project Reporting, Onsite and Offshore FTE should be fetched. Revenue should be fetched from Project Charter | Pending Integration / Testing / Server
Project Reporting | In Monthly Review, have Measurements, Contractual compliance, RAIDO. Remove others | Closed
Action Tracker | Action Tracker to be developed + Dashboard | Closed
DE Flow | DE assessment to be developed + Dashboard | Closed
General | Process to track whether weekly report and monthly reports are submitted. Provision to view defaulter at all levels | Closed
My Summary | My Summary pages to be improved. | Closed
Project Reporting | Measurement calculation to be implemented | Closed
Project Reporting | For Commitment and Milestone, Actual field to be captured. | Closed
Project Health | Develop Project Health dashboard. It should contain all reports and registers. {PROJECT LIST, RAG, RAIDO, METRICS, COMMITMENTS, PAYMENT MILESTONES, FINDINGS, ACTIONS, Data Integratyl etc}. Filters : Geo, Account, Project. | Closed
Amend Project | Add Applicable Phase should be added in Project Charter. Provision to select multiple phases with checkbox | Closed
Amend Project | In Project Amend section, project charter page, add Project Status combo (Ongoing, Hold, Closed, Open Only for Billing). | Closed
Maintain Project | Swap Leadership Support and Key Risks / Issues | Closed
Project Reporting | RAG Status - Change it to Tab. Provision to pull from projects | Closed
Account Head Flow | In Account Manager Dashboard -- http://localhost:3000/dashboard/account-manager, Project Governance Matrix - Rename Entity to Projects - Add Account Column before projects | Closed
My Summary | Account Manager Dashboard, PM Dashboard and Geo Head Dashboard should be rename as My Summary for all roles | Closed
Account Reporting | In Account-Reporting, Above Account Reporting, Add Account Dashboard (Readonly) . Same as PPT. | Closed
Project Reporting | Weeks should be populated with Monday date. | Closed
Geo Reporting | Implement geo reporting | Closed
CXO Flow | cxo login: change geo review to geo dashboard | Closed
Geo Flow | geo login: Add New Menu - Geo Dashboard | Closed
Account Head Flow | acc login: Add New Menu - Acc Dashboard | Closed
CXO Dashboard | Change the color to Blue. | Closed
Geo Dashboard | In Geo Dashboard, rename overview to Account Rollup | Closed
All | Standard - Dashboard, Reporting | Closed
Create Project | Project Creation + Oracle Projects - Project Creation. | Closed
Maintain Project | Remove Baseline Assessment from Create Project and Maintain Project menu. This is applicable only for Project Reporting. | Closed
All | Move AI Hub to top | Closed
DE Flow | DE Assessment - Alert should be removed. Finding should have Alert | Closed
Action Tracker | Action Tracker Implementation | Closed
Integrations | OneLogin Implementation | Deferred
Project Health | In Grid, Add Geo and Account Name | Closed
Project Health | Add Account RAG | Closed
Commitments Status | Breached should be added | Closed
My Summary | Health Split - Remove Red, Orange, Green text | Closed
My Summary | Open Actions - Use different color | Closed
Backend Loading | Product List to be loaded | Pending Integration / Testing / Server
General | Acc Head can do PM jobs, Geo Head can do PM and Acct Head Job | Closed
| Amend Functionality: Approved projects can be amended. All the fields except project type can be changed in amend. The value before amend is captured in Audit table. This Audit table is just for reference, no screen requried to view the changes.DE approval is requried in Amend. Edit Project button should be renamed as Amend Project. There is not send to approval button in Amend. All the Save <> should be renamed as Amend <>. Eg. Save Scope & Schedule should be called Amend Scope & Schedule. | Closed
| Valiations: On Approve: All the fields in Project Profile is mandatory In scope and schedule, All except project end date is mandatory All fields in measurement are mandatory There should be atleast one row in commitments and milestone RAIDO Registers are not mandatory. | Closed
| Show Geo - Region in all places. Title should be Geo Region | Closed
| There should be no restrict to approve and de assessment. It can be done any DE role. Name should be captured | Closed
| Project Status reporting, Revenue and other details should be defaulted from previous period | Closed
| Potential red should be handled in all places | Closed
| DE Flow should be changed. DE reporting to have DE Assement Date. | Closed
| DE - View Project to be developed | Closed
| Findings - Category. Align with RAG | Closed
| Validations for Measurements. Range. Now I can give 200% for percentage measure | Closed
| DE Assessment - Remove This Month and Last Assessment. Last Assessment date should be shown with Due | Closed
| Finding should be at project level | Closed
| Add DE findings in the left hand side. Findings can be created with or without assessment | Closed
| There should be a provision to view previous assessment | Closed
| For Partial Project Profile, % is not computed properly | Closed
| In project profile, delivery manager should be defaulted | Closed
| In Scope, Plan End date is mandatory | Closed
| Mandatory * to be added without validations | Closed
| New Commitment and payment milestones can be added only in Amend. Remove Add functionality from Project Reporting | Closed
| In New Project, Remove right side menu. http://localhost:3000/new-project/new/create | Closed
| Move Maintain project next to New Project | Closed
| Create Project, Provide Project Details, Amend Project Details, Report Project Status, Project Dashboard - PM Menu | Closed
| Weekly Report - Delivery Status Reporting (Weekly) Monlthly Report - Metrics Reporting (Monthly) | Closed
| VAPT testing | Pending Integration / Testing / Server
| Functional Testing | Pending Integration / Testing / Server
| Server Provisioning | Pending Integration / Testing / Server
| Project Team Testing | Pending Integration / Testing / Server
| Load Account and User details. Check all admin page data | Pending Integration / Testing / Server
| Finding should be added as Left Side menu for PM. | Closed
| Finding total should be shown to Account Head, Geo Head and CXO | Closed
| For Metics validation, Need lower limit, upper limit and breach limit. When the value is greater than breach limit, what should we do? | Closed
| Finding will be raised against Project, no assignee is requried | Closed
| Findings - Current classificaiton should be called Category. New Classificaiton - Observation/ Recommendation/NC. Remove Criticality | Closed
| PM Menu - Rename Findings as DE Findings | Closed
| PM Findings - Remarks to be renamed as Action Taken. Add Action Taken Date | Closed
| DE Findings Closure - Add Closure Date, Verification Remarks. Remove Save Changes. Add Reopen Findings | Closed
| Applicable Phases - Discovery / POC / Assessment / Consulting (First) , Migration (Last) , UAT to UAT Support | Closed
| In http://localhost:3000/project-health/project-list, Add Region and Ownership in Filter and grid | Closed
| http://localhost:3000/project-health/findings - Add Classification filter and Over Due and Non Over Due Filter. | Closed
| Project health grid should have download to excel feature | Closed
| Against a commitment, there should be a provision to record multiple actuals | Closed
| In Account Reporting and Geo Reporting, Remove monthly reporting | Closed
| Executive Risk Dashboard | Pending with Quality
| Not submitted - Red, Submitted - Green. This is for all reports | Closed
| Project, Account, Geo should have Governance Tool Implementation Effective Date. Pending reports should be computed based on this date | Closed
| Weekly Reporting and Monthly reporting should be replaced with Delivery reporting and Metric reporting | Closed
| NC should renamed as Alert | Closed
| Delivery Status Reporting is the common name. Tag Project, Account or Geo | Closed
| In DE Projects Measurements should have Reporting period, Contractual compliance - Actual value to be displayed, | Closed
| RAIDO register should have filter in PM and DE Views | Closed
| In Findings all fields are mandatory | Closed
| In Findings Page, Project should be auto complete text box instead of combo | Closed
| In all project filters, add Geo, Region, Account, Type and Ownership | Closed
| In Compliance, Status Breached should be removed. penality column should be shown in compliance history grid | Closed
| PM Assignment AutoText to be moved to Create Project Details. PM in create project details should be Readonly | Closed
| Assignment of roles and names for Geo, Account and Project should be provided for Geo Heads and DE | Closed
| Create project should be enabled only for Geo Head and Acc Heads | Closed
| Create Project - Workflow Approval to DE | Closed
| Archive Project for DE should be enabled | Pending - Last
| Project Health should have report submissions summaries | Closed
| Notification in App functionality to be implemented | Closed
| In Measurement - Metrics Target, info icon should be shown | Closed
| In Measurement - Metrics Target, Productivity UOM should be loaded from config. It is displayed wrongly | Closed
| In Measurement - Metrics Target, Benchmark value should be loaded from config | Closed
| In Create Project, PM combo should be filtered combo | Closed
| In DE Menu, rename Project Creation Requests to Project Creation Approval and DE Approval to Project Details Approval | Closed
| For Accounts, Region should be captured. | Closed
| In DE Menu, rename Projects as View Projects and Project Health as View Project Health | Closed
| Tool Name, Login page, BCT Logo and Tag line to be added | Pending - Last
| Change password and forgot password feature to be implemented | Closed
| Project Creation Approval and Rejection should have Remarks | Closed
| When Project is Created, Org, Geo, Region and Account to be fetched based on Oracle Id, can be changed before saving | Pending Integration / Testing / Server
| In Development Metrics, Size Unit - Add Story Point. On change of Size Unit, Productivity should be changed | Closed
| In Development Metrics, Overall Effort esmitate, unit should be person-day | Closed
| Commitment should have UOM as textbox | Closed
| DE Allocation is not mandatory. Project Details Approval can be done without DE | Closed
| When Project is rejected, Rejection remarks should be shown. DE status should be shown in the Grid | Closed
| Notifcation to be checked | Pending - Last
| When the Project is Approved, the lifecycle status should be OnGoing | Closed
| Open Alerts till the reporting period should be brought in the dashboards. After submission, the report should be frozen, values should not change | Closed
| Project Reporting, There should be a provision to resubmit the project report after rejection | Closed
| DE Assessment Report should be added in PM View. Same as http://192.168.1.175:3000/de-assessment/4f2e19c4-7b99-4ddf-bfb9-49a97d7c0ae2. All fields readonly | Closed
| Metics report should be renamed as Project Performance Report. There is not approval process. In all pages, Reviewed and No Changes button to added. This marks the completion of the review process | Closed
| Project Performance Dashboard to be developed | Closed
| In Account Manager view, Project Dashboard to be renamed as Delivery Status Report. New Menu, Project Performance Report to be added | Pending
| In DE Allocation, there should be a provision to fetch DE allocated project and DE can be changed any time. | Closed
| In Account Reporting, Submit Report should be enabled only from Dashboard. It should be removed from Account Status. This should be done for Geo Reporting also | Closed
| In Account Reporting main page, Report status should be rejected for Rejected reports. There should be a provision to resubmit the rejeccted report. Check for Project Reporting and Geo Reporting | Closed
| CXO should be renamed as CDO | Closed
| In All Pages, Project Dashboard should be renamed as Delivery Status Report & Project Performance Report | Pending
| Action Flow - | Pending
| New Action Creation / View Page from Left Menu | Pending
| DE Menu - Project Health - To view project , account , geo reports | Pending

## Defects
Description | Status
In Geo Head Reporting, Executive update is not launching. In 175 server, this issue is simulated | Completed
Project Performance Dashboard -- from View pages, back should take to main page. Breadcrumb to be updated | Pending

## Scope
Project Type | Description
Development/ Implementation/ Enhancement | Fixed-price or Time & Material software development/ enhancement projects
Support (Application/ Infrastructure) | Incident, service request, bug fixes, enhancements, SLA monitoring, Continuous IT operations, monitoring, infrastructure, SOC/NOC, helpdesk
Professional Staffing | Resource deployment, timesheets, billing, contracts, utilization
Testing | Executing test cases, tracking defects, performing regression testing, and verifying system performance, security, and usability
Cloud Maintenance | Monitoring system uptime, applying security patches, managing user access, backing up data, and optimizing infrastructure costs.
Cloud Migration | Assessing existing architecture, planning data transfers, refactoring applications for the cloud, and securely cutting over traffic.

## Dash board
Dashboard
Active Projects
Projects by Type
Delayed Projects
Open Risks
Open Issues
Pending Approvals
Project Health ( Covers 360 View of a project for Delivery Review)
Account Health
Contractual Commitment
Milestones Linked to Payment

## Project Charter
Project Description |  | Progress |  | Resource Allocation <To be pulled from BCT Oracle App > |  | Treatment
Project Name | <To fill Project Name> | <Planned Start Date> | <Actual Start Date> | Resource1 | 1 FTE | Applicable Phase | <Reqm/ Design/ CUT/ Build & Deployment/ Testing/UAT/Warranty/ Support> | <Description>
Project ID | <Auto Generated> | <Planned End Date> | <Actual End Date> | Resource2 | 0.5 FTE | Delivery Declared Project Health | Overall Auto Calculated, even if one parameter is red, the overall rating shall be red. Core Delivery - <Red/ Potential Red/ Amber/ Green> (Scope/ Cost/ Scheule/ Quality/ Contractual SLA/ KPI) People - <Red/ Potential Red/ Amber/ Green> (Resourcing/ Fulfilment/ Skilling/ Performance/ Attrition) Operational - <Red/ Potential Red/ Amber/ Green> (PID Creation/ Extension/ Contract Extension/PO/ Projects without contract/ Payment / Invoices/ Timesheet) Customer - <Red/ Potential Red/ Amber/ Green> (Relation/ Pulse/ Feedback/ Opportunities/ Business) Financial - <Red/ Potential Red/ Amber/ Green> - (Forecast/ Margin/ MIP) Compliance - - <Red/ Potential Red/ Amber/ Green> - (Security/ Infrastructure/ Vendor Management) | <Delivery Description>
Contract Type | FPP/ TM/ Capped TM/ Internal <Data to be updated from PMO Input> | <Planned Duration> | <Actual Duration> | Resource3 | 0.25 FTE | Delivery Declared Overall Project Health | <Red/ Potential Red/ Amber/ Green> - Auto Calculated
Project Type | <Development/ Maintenance/ Professional Staffing/Support (Application/ Infrastructure)/ Testing/ Cloud Maintenance/ Cloud Migration> |  |  | Resource4 | 1 FTE | DE Assessed Project Health | <Red/ Potential Red/ Amber/ Green> - Static <Pulled form DE Assessment Sheet> | <DE Description>
Organization | BCTPL/BCTC/ FT <Data to be updated from PMO Input> |  |  | Resource5 | 1 FTE | Project Status | <Start Up/ Execution/ Hold/ Closed/ Open Only for Billing> | <Description>
Project Owned | Fully Owned/Co-Owned/ Customer Driven |  |  | Resource6 | 1 FTE | Overall Project Health | <Red/ Potential Red/ Amber/ Green> | Infered from highest status
GEO | <APAC/ MEA/ US> <Data to be updated from PMO Input> |  |  | Resource7 | 1 FTE
Account Name | <To fill Account Name> |  |  | Resource8 | 1 FTE
Project Manager | <Name of the PM> |  |  | Resource9 | 1 FTE
Delivery Manager | <Name of the Delivery Manager>
Delivery Excellence | <Name of the Delivery Excellence> |  |  | Head Count | <Auto Calculated from Resource>
Customer Overview | < Describe Customer Business and landscape> |  |  | FTE | <Auto Calculated from Resource>
Customer Sponsor | < Customer Sponsor Name>
Customer Sponsor Mail Id | <Customer Sponsor Mail Id>
Customer Program Head | < Customer Program Head Name>
Customer Program Head Mail Id | <Customer Program Head Mail Id>
Customer SPOC | < Customer SPOC Name>
Customer SPOC Mail Id | <Customer SPOC Mail Id>
Project Scope Description | <Project Scope & Short Description>
Project Revenue
Project Currency
Oracle Project IDs

## Project Status
Project Status
Project Current Status | Description
Key Accomplishments | <Provide the accomplishments from last report to now, including client appreciations in the form of bullets>
UPCOMING KEY RELEASES/ MILESTONES/ ACTIONS | <Provide Upcoming key activities to focus in the form of bullets>
LEADERSHIP SUPPORT/ ATTENTION REQUIRED | <Provide the areas where leadership support is required – in the form of bullets>

## Measurement
Development Projects | [8 empty] | Metric Formula, Operational Definition and Recommended Benchmark
Measure | Catergory |  |  | Unit of Measure | Metrics |  | Unit | Mandatory | Formula | Operational Definition | Benchmark Value
| High | Medium | Low
Oveall Planned Size | NA | NA | NA | CP/ FP/ LOC/ Other | Productivity |  | Size/ Person-Day | Y | Actual Size / Actual Effort (person-days) | Delivery output completed and accepted per person-day. Use one consistent sizing method (CP, FP, LOC or approved alternative) for planned and actual values. | Within -0.4 to 5 CP/ Manday. 0.45 CP/ Manday
Actual Size (End of the Project) | NA | NA | NA | CP/ FP/ LOC/ Other | Effort Variation |  | % | Y | ((Actual Effort - Estimated Effort) / Estimated Effort) x 100 | Percentage deviation of final or forecast actual effort from the approved estimate. Positive values indicate overrun; negative values indicate underrun. | Within -10% to +10%; investigate when absolute variation exceeds 10%.
Overall Estimated Effort | NA | NA | NA | Person-Hourss | Schedule Performance Index (SPI) |  | No Unit | Y | Earned Value (EV) / Planned Value (PV) | Schedule efficiency as of the reporting date. EV is budgeted effort for work completed; PV is budgeted effort planned to be completed. | Green: >= 0.95; Amber: 0.90-0.94; Red: < 0.90. Values > 1.00 indicate ahead of plan.
Planned Effort (As on Date) | NA | NA | NA | Person-Hourss | Cost Performance Index (CPI) |  | No Unit | Y | Earned Value (EV) / Actual Cost (AC) | Cost efficiency as of the reporting date. Where cost data is unavailable, approved effort-hours may be used consistently as the cost proxy. | Green: >= 0.95; Amber: 0.90-0.94; Red: < 0.90. Values > 1.00 indicate favorable efficiency.
Actual Effort (As on Date) | NA | NA | NA | Person-Hourss | Defect Leakage(Internal Vs External) |  | % | Y | External Defects / (Internal Defects + External Defects) x 100 | Proportion of total defects detected after release to UAT, customer validation or production, based on the project's agreed internal/external defect boundary. | <= 5%; stretch target <= 3%.
Planned % of Completion (As on Date) | NA | NA | NA | % | Code Coverage ( Tool Based ) |  | % | N | Covered Code Elements / Total Applicable Code Elements x 100 | Percentage of applicable source-code statements, branches or lines executed by automated tests, using the approved code-quality tool and stated coverage type. | >= 80% overall and >= 90% for critical modules; no reduction below contractual target.
Actual % of Completion (As on Date) | NA | NA | NA | % | Test Execution Coverage (%) |  | % | Y | Executed Test Cases / Planned Test Cases x 100 | Percentage of approved in-scope test cases executed during the reporting cycle or test phase. | >= 95% by test-cycle closure; 100% for critical and committed test cases.
URD Defects - Internal |  |  |  | Count | Test Pass Rate (%) |  | % | Y | Passed Test Cases / Executed Test Cases x 100 | Percentage of executed test cases with Pass status, excluding blocked or not-run cases from the denominator. | >= 95% overall and 100% for critical business scenarios before release.
URD Defects - External |  |  |  | Count
Proto Defects - Internal |  |  |  | Count
Proto Defects - External |  |  |  | Count
SRS Defects - Internal |  |  |  | Count
SRS Defects - External |  |  |  | Count
ADD Defects - Internal |  |  |  | Count
ADD Defects - External |  |  |  | Count
HLD Defects - Internal |  |  |  | Count
HLD Defects - External |  |  |  | Count
USP/ LLD Defects - Internal |  |  |  | Count
USP/ LLD Defects - External |  |  |  | Count
Code Defects - Internal |  |  |  | Count
Code Defects - External |  |  |  | Count
UTC Defects - Internal |  |  |  | Count
UTC Defects - External |  |  |  | Count
SITC Defects - Internal |  |  |  | Count
SITC Defects - External |  |  |  | Count
UT Defects - Internal |  |  |  | Count
UT Defects - External |  |  |  | Count
SIT Defects - Internal |  |  |  | Count
SIT Defects - External |  |  |  | Count
UAT Defects - External |  |  |  | Count
Production Defects - External |  |  |  | Count
Total Number of Test Cases Designed |  |  |  | Count
# of Executed Test Cases | NA | NA | NA | Count
# of Passed Test Case | NA | NA | NA | Count
Last Updated Date < Default Date to be Displayed> | NA | NA | NA
Support ( Application/ Infrastructure)
Measurement |  |  |  |  | Metrics |  | Unit |  | Formula | Operational Definition | Benchmark Value
Ticket Type | Catergory | Unit of Measure |  |  | Incident (P1/P2/P3) - SLA Compliance % |  | % |  | Incidents Resolved Within SLA / Total SLA-Applicable Incidents x 100 | Percentage of SLA-applicable incidents resolved within the applicable priority-specific contractual resolution time. Report separately for P1, P2 and P3. | P1 >= 99%; P2 >= 98%; P3 >= 95%, or the higher contractual SLA.
Incidents | P1 | Count | Person-days |  | Incident (P1/P2/P3) - MTTR |  | Person-Hours/ # of Incidents |  | Total Incident Resolution Time / Number of Resolved Incidents | Average elapsed time from incident logging to restoration/resolution, excluding only formally approved SLA pause periods. Report by priority. | P1 <= 4 hours; P2 <= 8 hours; P3 <= 24 hours, or within contractual MTTR.
| P2 | Count | Person-days |  | Service Request - MTTR |  | Person-Hours/ # of SR |  | Total Service Request Fulfilment Time / Number of Fulfilled Service Requests | Average elapsed time from service-request logging to fulfilment, excluding formally approved waiting or hold periods. | <= 2 business days overall, or within the priority/category-specific contractual target.
| P3 | Count | Person-days |  | User Clarification- MTTR |  | Person-Hours/ # of UC |  | Total Clarification Resolution Time / Number of Closed User Clarifications | Average elapsed time from clarification logging to provision and acceptance of a complete response, excluding approved customer-wait time. | <= 1 business day overall; critical clarification response <= 4 business hours.
Service Request | NA | Count | Person-days
User Clarification | NA | Count | Person-days
# of Ticket Re-Opened | NA | Count
# Of Aging Tickets | NA | Count
# Of First Time Resolution | NA | Count
Professional Staffing
Measure |  | Units |  |  | Metrics |  | Units |  | Formula | Operational Definition | Benchmark Value
No of request | NA | Count |  |  | Average Response Time to a request for resources | Critical (P1) | Person-Hours/ # of Resource Request |  | Sum of First Response Times / Number of Resource Requests | Average elapsed time from receipt of a complete resource request to the first qualified response or acknowledgement. Calculate separately by priority. | P1 <= 4 hours; P2 <= 8 hours; P3 <= 1 business day; P4 <= 2 business days.
Response Time to a request for resources | Critical (P1) | Person-Hours |  |  |  | High (P2) | Person-Hours/ # of Resource Request
| High (P2) | Person-Hours |  |  |  | Medium (P3) | Person-Hours/ # of Resource Request
| Medium (P3) | Person-Hours |  |  |  | Low (P4) | Person-Hours/ # of Resource Request
| Low (P4) | Person-Hours |  |  | Percentage of profiles that Qualify for Client Submissions (Profile submission vs Client Interview ) |  | % |  | Profiles Progressing to Client Interview / Profiles Submitted x 100 | Percentage of submitted candidate profiles accepted by the client for interview; measures quality and fit of profile screening. | >= 60%; stretch target >= 70%.
# of Profiles Submitted | NA | Count |  |  | Percentage of candidates that result in Joining (Interview Selects v Joined) |  | % |  | Associates Joined / Interview Selects x 100 | Percentage of candidates selected after interview who complete onboarding and join within the agreed validity period. | >= 85%; stretch target >= 90%.
# of Client Interviews | NA | Count |  |  | Lead Time - Resource Request to Onboarding | Critical (P1) | Person-Days/ # of Onboarding |  | Sum of (Onboarding Date - Request Date) / Number of Associates Onboarded | Average elapsed business days from receipt of a complete and approved resource request to associate onboarding. Report separately by priority. | P1 <= 10 business days; P2 <= 15; P3 <= 20; P4 <= 30, subject to skill scarcity and contract.
# of Interview Selects | NA | Count |  |  |  | High (P2) | Person-Days/ # of Onboarding
# of Associates Joined | NA | Count |  |  |  | Medium (P3) | Person-Days/ # of Onboarding
Lead Time - Resource Request to Onboarding | Critical (P1) | Person-Days |  |  |  | Low (P4) | Person-Days/ # of Onboarding
| High (P2) | Person-Days
| Medium (P3) | Person-Days
| Low (P4) | Person-Days
Testing
Measurements | Unit |  |  |  | Metric |  | Unit |  | Formula | Operational Definition | Benchmark Value
Total Number of Test Cases Designed | Count |  |  |  | Test Execution Coverage (%) |  | % |  | Executed Test Cases / Planned Test Cases x 100 | Percentage of approved in-scope test cases executed in the test cycle or reporting period. | >= 95% by cycle closure; 100% for critical and committed scenarios.
# of Executed Test Cases | Count |  |  |  | Test Pass Rate (%) |  | % |  | Passed Test Cases / Executed Test Cases x 100 | Percentage of executed test cases with Pass status; blocked and not-run cases are excluded from the denominator and reported separately. | >= 95% overall; 100% for critical scenarios before sign-off.
# of Passed Test Case | Count |  |  |  | Automation Coverage (%) |  | % |  | Automated Test Cases / Automation-Eligible Test Cases x 100 | Percentage of technically and economically automation-eligible regression test cases implemented and successfully executable through approved automation tools. | >= 70% of eligible regression suite; >= 80% for stable critical regression flows.
# of Test Case Automated | Count |  |  |  | Test Design Productivity |  | # of Test Case Designed/ Person-Days |  | Test Cases Designed / Test Design Effort (person-days) | Number of reviewed and baselined test cases designed per person-day, including required test data and traceability. | >= approved organizational baseline; initial planning range 8-12 test cases/person-day.
Effort Spent for Test Case Design | Person-Days |  |  |  | Test Execution Productivity |  | # of Executed Test Cases/ Person-Days |  | Executed Test Cases / Test Execution Effort (person-days) | Number of test cases executed and evidence recorded per person-day. Re-runs should be identified separately to avoid double counting. | >= approved organizational baseline; initial planning range 15-25 test cases/person-day.
Effort Spent for Test Execution | Person-Days
Cloud Maintenance Project
Measurements | Unit |  |  |  | Metrics |  | Unit |  | Formula | Operational Definition | Benchmark Value
Total Uptime | Person-Days |  |  |  | Service Availability (%) |  | % |  | (Total Scheduled Service Time - Service Downtime) / Total Scheduled Service Time x 100 | Percentage of agreed service hours during which the cloud service is available, excluding only approved maintenance windows where permitted by contract. | >= 99.9% monthly, or the higher contractual target.
Total Scheduled Time | Person-Days |  |  |  | Application Availability (%) |  | % |  | (Total Scheduled Application Time - Application Downtime) / Total Scheduled Application Time x 100 | Percentage of agreed service hours during which the application is usable end-to-end, excluding only approved maintenance windows where permitted. | >= 99.5% monthly; critical applications >= 99.9%, or contractual target.
Application Downtime | Person-Days
Cloud Migration Projects
Measurements | Units |  |  |  | Metrics |  | Unit |  | Formula | Operational Definition | Benchmark Value
Planned Application Migration | Count |  |  |  | Applications Migrated ( Planned Vs Actual) |  | % |  | Applications Migrated / Planned Applications for the Period x 100 | Percentage of applications planned for migration in the approved wave or reporting period that completed cutover and acceptance. | >= 95% per migration wave; 100% by committed program milestone.
Applications Migrated | Count |  |  |  | Migration Success Rate ( Success Vs Total) |  | % |  | Successful Migrations / Total Migration Attempts x 100 | Percentage of migration attempts completing cutover, validation and acceptance without rollback or severity-1 migration failure. | >= 98%; target 100% for business-critical applications.
Total Migration Attempts | Count |  |  |  | Migration Downtime |  | Person-Hours |  | Migration End Date-Time - Migration Start Date-Time | Elapsed time from approved migration start to completed cutover and service validation. Planned exclusions must be documented. | Within approved migration window and <= planned downtime; recommended critical-service target <= 2 hours.
Successful Migrations | Count
Migration End Time | Date and Time
Migration Start Time | Date and Time
[9 empty] | Benchmark Note | Benchmarks are recommended initial governance thresholds. Approved contractual SLAs, customer commitments, regulatory requirements and calibrated organizational baselines take precedence.

## Contractual Compliance
Contractual Commitment Definition
Frequency | Name of the Commitment | Formula | Target | Penalty Applicable | Penalty Value
One Time/Weekly/ Fortnight/ Monthly/ Quaterly/ Half Yearly/ Phase Wise |  |  |  | Yes/ No
Contractual Commitment Actual
Frequency | Name of the Commitment | Formula | Target | Penalty Applicable | Penalty Value | Actual | Met/ Not Met
Static | Static | Static | Static | Static | Static
Milestones Linked to Payment Definition
Milestone Name | Milestone Description | Expected Date of Payment | Expected Payment Value
Milestones Linked to Payment Actual
Milestone Name | Milestone Description | Expected Date of Payment | Expected Payment Value | Actual Date of Payment | Actual Payment Value | Status | Remarks
Static | Static | Static | Static |  |  | Paid On Time/ Delayed Payment/ Yet To Be Paid

## Risk
Field | Description
Risk ID | Unique identifier | Auto Generated
Project Name | Related project | Default
Project Type | <Development/ Maintenance/ Professional Staffing/Support (Application/ Infrastructure)/ Testing/ Cloud Maintenance/ Cloud Migration> | Default
Risk Title | Short description
Risk Description | Detailed explanation
Risk Category | Core Delivery / People /Operational / Customer / Financial / Compliance
Risk Type | Internal / External
Identified By | Person identifying the risk
Identified Date | Date recorded
Risk Owner | Responsible person
Trigger/Event | Event indicating the risk may occur
Probability | Very Low, Low, Medium, High, Very High
Impact | Very Low, Low, Medium, High, Critical
Risk Score | Probability × Impact
Severity | Low, Medium, High, Critical
Affected Deliverables | Deliverables at risk
Affected Milestone | Related milestone
Response Strategy | Avoid, Mitigate, Transfer, Accept
Mitigation Plan | Preventive actions
Contingency Plan | Actions if the risk occurs
Residual Risk | Remaining risk after mitigation
Target Resolution Date | Planned completion
Current Status | Open, Monitoring, Closed
Escalation Required | Yes / No
Escalated To | Higher authority
Last Review Date | Latest review
Next Review Date | Planned review
Closure Date | Date closed
Remarks | Notes

## Opportunity
Field | Description
Opportunity ID | Unique identifier
Project Name | Related project
Project Type | <Development/ Maintenance/ Professional Staffing/Support (Application/ Infrastructure)/ Testing/ Cloud Maintenance/ Cloud Migration>
Opportunity Title | Short description
Opportunity Description | Detailed explanation
Category | Core Delivery / People /Operational / Customer / Financial / Compliance
Identified By | Person identifying the opportunity
Identified Date | Date recorded
Opportunity Owner | Responsible person
Impact | Very Low, Low, Medium, High
Expected Benefit | Time, Cost, Quality, Revenue
Estimated Benefit | Quantified value
Benefit Type | Cost Saving, Revenue Increase, Quality Improvement, Customer Satisfaction
Exploitation Strategy | Exploit, Enhance, Share, Accept
Action Plan | Planned actions
Target Implementation Date | Planned completion
Status | Identified, Approved, Implemented, Closed
Approval Required | Yes / No
Approved By | Approver
Actual Benefit | Realized outcome
Closure Date | Date completed
Remarks | Notes

## Dependencies
Field | Description
Dependency ID | Unique identifier
Project Name | Related project
Project Type | <Development/ Maintenance/ Professional Staffing/Support (Application/ Infrastructure)/ Testing/ Cloud Maintenance/ Cloud Migration>
Dependency Title | Short description
Description | Detailed dependency
Dependency Type | Internal, External, Vendor, Customer, Infrastructure, Regulatory, Third Party
Category | Core Delivery / People /Operational / Customer / Financial / Compliance
Depends On | Team, task, project, vendor, or customer
Related Task/Milestone | Linked project activity
Required By | Needed before this date
Owner | Responsible person
Dependency Status | Not Started, In Progress, Completed, Blocked
Criticality | Low, Medium, High, Critical
Impact if Delayed | Expected consequence
Probability of Delay | Low, Medium, High
Mitigation Plan | Risk reduction action
Escalation Required | Yes/No
Escalation Level | Project Manager, Delivery Manager, Steering Committee
Actual Completion Date | When dependency was completed
Last Updated | Last modification date
Remarks | Additional comments

## Issues
Field | Description
Issue ID | Unique identifier
Project Name | Related project
Project Type | <Development/ Maintenance/ Professional Staffing/Support (Application/ Infrastructure)/ Testing/ Cloud Maintenance/ Cloud Migration>
Issue Title | Short description
Issue Description | Detailed explanation
Issue Category | Core Delivery / People /Operational / Customer / Financial / Compliance
Priority | Low, Medium, High, Critical
Severity | Minor, Major, Critical
Raised By | Person reporting the issue
Raised Date | Date reported
Assigned To | Responsible person
Root Cause | Underlying cause
Business Impact | Effect on project
Affected Deliverables | Deliverables impacted
Affected Milestone | Related milestone
Resolution Plan | Planned solution
Due Date | Target resolution date
Actual Resolution Date | Completion date
Status | New, Assigned, In Progress, Pending, Resolved, Closed
Escalation Level | PM, Delivery Manager, Steering Committee
Escalation Date | Date escalated
Resolution Summary | Final resolution
Lessons Learned | Preventive improvements
Closure Date | Date closed
Remarks | Notes

## Assumption
Field | Description
Assumption ID | Unique identifier
Project Name | Related project
Project Type | <Development/ Maintenance/ Professional Staffing/Support (Application/ Infrastructure)/ Testing/ Cloud Maintenance/ Cloud Migration>
Title | Short description
Detailed Description | Full assumption statement
Category | Core Delivery / People /Operational / Customer / Financial / Compliance
Raised By | Person who recorded the assumption
Raised Date | Date created
Owner | Responsible person
Dependency Reference | Linked dependency (optional)
Impact if Invalid | Consequences if assumption fails
Probability of Failure | Low / Medium / High
Impact Rating | Low / Medium / High / Critical
Validation Date | Planned review date
Validation Status | Pending, Validated, Invalid
Mitigation Plan | Action if assumption proves false
Contingency Plan | Backup plan
Current Status | Open, Closed, Cancelled
Last Updated | Last modification date
Remarks | Additional comments

## DE Assessment Form
DE Assessment Form
DE Assessed Project Health | <Red/ Potential Red/ Amber/ Green> | if not green | Alert ID
Alert Category <Core Delivery / People /Operational / Customer / Financial / Compliance>
Alert Brief description
Detailed Description
Raised By
Raised On
PCI Score
Key Findings | 1 | Classification<Observation/ Recommendation> | Action Taken | Date | Status (Open/ Closed/ On Hold/ Deferred) | Remarks (if Any)
2
3

## Data Integrity
Data | Status
Planned Size | Updated/ Not Updated
Actual Size | Updated/ Not Updated
Planned Effort | Updated/ Not Updated
Actual Effort | Updated/ Not Updated
Planned % of Completion | Updated/ Not Updated
Actual % of Completion | Updated/ Not Updated
URD Defects - Internal | Updated/ Not Updated
URD Defects - External | Updated/ Not Updated
Proto Defects - Internal | Updated/ Not Updated
Proto Defects - External | Updated/ Not Updated
SRS Defects - Internal | Updated/ Not Updated
SRS Defects - External | Updated/ Not Updated
ADD Defects - Internal | Updated/ Not Updated
ADD Defects - External | Updated/ Not Updated
HLD Defects - Internal | Updated/ Not Updated
HLD Defects - External | Updated/ Not Updated
USP/ LLD Defects - Internal | Updated/ Not Updated
USP/ LLD Defects - External | Updated/ Not Updated
Code Defects - Internal | Updated/ Not Updated
Code Defects - External | Updated/ Not Updated
UTC Defects - Internal | Updated/ Not Updated
UTC Defects - External | Updated/ Not Updated
SITC Defects - Internal | Updated/ Not Updated
SITC Defects - External | Updated/ Not Updated
UT Defects - Internal | Updated/ Not Updated
UT Defects - External | Updated/ Not Updated
SIT Defects - Internal | Updated/ Not Updated
SIT Defects - External | Updated/ Not Updated
UAT Defects - External | Updated/ Not Updated
Production Defects - External | Updated/ Not Updated
Total Number of Test Cases Designed | Updated/ Not Updated
# of Executed Test Cases | Updated/ Not Updated
# of Passed Test Case | Updated/ Not Updated
Incidents details | Updated/ Not Updated
Service Request details | Updated/ Not Updated
User Clarification details | Updated/ Not Updated
# of Ticket Re-Opened | Updated/ Not Updated
# Of Aging Tickets | Updated/ Not Updated
# Of First Time Resolution | Updated/ Not Updated
No of request | Updated/ Not Updated
Response Time to a request for resources | Updated/ Not Updated
# of Profiles Submitted | Updated/ Not Updated
# of Client Interviews | Updated/ Not Updated
# of Interview Selects | Updated/ Not Updated
# of Associates Joined | Updated/ Not Updated
Lead Time - Resource Request to Onboarding | Updated/ Not Updated
Total Number of Test Cases Designed | Updated/ Not Updated
# of Executed Test Cases | Updated/ Not Updated
# of Passed Test Case | Updated/ Not Updated
# of Test Case Automated | Updated/ Not Updated
Effort Spent for Test Case Design | Updated/ Not Updated
Effort Spent for Test Execution | Updated/ Not Updated
Total Uptime | Updated/ Not Updated
Total Scheduled Time | Updated/ Not Updated
Application Downtime | Updated/ Not Updated
Planned Application Migration | Updated/ Not Updated
Applications Migrated | Updated/ Not Updated
Total Migration Attempts | Updated/ Not Updated
Successful Migrations | Updated/ Not Updated
Migration End Time | Updated/ Not Updated
Migration Start Time | Updated/ Not Updated
Risk | Updated/ Not Updated
Assumption | Updated/ Not Updated
Opportunity | Updated/ Not Updated
Dependencies | Updated/ Not Updated
Issues | Updated/ Not Updated
Delivery Declared Project Health | Updated/ Not Updated
DE Assessed Project Health | Updated/ Not Updated
Project Status | Updated/ Not Updated
Contractual Commitment Definition | Updated/ Not Updated
Contractual Commitment Actual | Updated/ Not Updated
Milestones Linked to Payment Definition | Updated/ Not Updated
Milestones Linked to Payment Actual | Updated/ Not Updated

## Integration
Integrate with:
Microsoft 365
BCT Oracle Application
Ticketing Tools
Existing Project Management tools

## Security
Features:
Role-Based Access Control (RBAC)
Multi-Factor Authentication (MFA)
Audit Trail
Activity Logs
Data Encryption
Backup and Restore

## Login
Login Screen
Access for the following roles
Admin
CEO/ CDO/ GEO Head/ Delivery Manager
Project Manager
| User Name : | Project Team Member
| Password : | Delivery Excellence
PMO
LDAP to be Implemented

## Action
SNO | Actions | Status
1 | Clean Up the Sheets | Completed
2 | Architecture | Completed
3 | Name the Tool (Not Project Management, more from project governance) | Yet To Start
4 | Discuss with Hariharasudhan | Completed
5 | Discuss with Geo Heads | Completed
6 | Discuss with Vivek | Completed
7 | Discuss with Sowmya/ Revathi | Yet To Start
8 | Discuss with Venkat | Yet To Start

## Requirements Elaboration
Sno | Screen | Input | Requirement Elaboration | Status
1 | Project Charter | Shaik/ Ajith | We require data from oracle to be pulled based on oracle ID (mainly resources from multiple oracle project id’s) and other fields can be directly from one project. In this context, we need to have the oracle id as the first field in the form. We will get this oracle id’s in excel validated before data migration from oracle. | To be Discussed
2 | Dashboard/ Project Charter/ Measurement | Vivek Puri | OTL Dashboard and PO - to be discussed with Venkat | To be Discussed
3 | Project Charter | Vivek Puri | Customer Hirarchy - Stakeholder involved | Taken Up
4