## ISO 20000 Estimation Inputs
PDO ISO/IEC 20000-1 Estimation Inputs
Input updated from PDO ISO20000-1 Proposal Questionnaire Section 1 and service estimation workbook
Company Name: |  | Petroleum Development Oman LLC (PDO)
Address: |  | P.O. Box 81, P.C. 100, Muscat, Sultanate of Oman
Site 1 (Head Office): |  | PDO Head Office, Mina Al Fahal, Saih Al Malih, Muscat, Oman
Source Questionnaire: |  | PDO_ISO20000-1_Proposal_Questionnaire_Section1_Filled
Scope |  | Provision, management, support, monitoring, and continual improvement of enterprise IT services delivered by PDO's Information Technology Directorate (IDD), including Infrastructure Services, End User Support, Application Support, Cloud Services, Data Centre Services, Network Services, SAP Services, Cybersecurity Operations, Field Communication Systems, and Digital Platforms supporting PDO operations.
Certification Boundary: |  | IDD / IT Directorate only. Services and processes managed outside IDD are excluded from the ISO/IEC 20000-1 certification boundary.
Included Service Groups: |  | Infrastructure Services; End User Support; Cloud Services; Application Support; Field Communication Systems; Data Centre; SAP Support; Network Services; Digital Platforms; Cyber Security Operations.
Scope Exclusions / Limitations: |  | Operational Technology (OT) services are excluded. Non-IDD managed services/processes and external stores/warehouses outside PDO-controlled premises are excluded unless formally added to scope.
Location / Site Coverage: |  | Primary site: PDO Head Office, Mina Al Fahal / Saih Al Malih, Muscat, Oman. Remote/operational sites and travel/audit sampling locations to be confirmed by PDO during mobilisation.
S.No | Service Name | Total Resource Involved in Scope | Description of Service | Complexity Multiplier
1 | Infrastructure Services | 15+ | Hosting, Database, Storage, Back-up, AD, etc. | 1
2 | End User Support | 50+ | ServiceDesk & Hardware & Asset Management | 1
3 | Cloud Services | Scattered across Apps Team | Cloud Hosting coordination services | 1
4 | Application Support | 50+ (incl. Contractors) | App Development, testing, run & maintain | 1
5 | Field Communication Systems | 10+ | WiMAX & Tetra Services | 1
6 | Data Centre | 7+ | Data Center Facilities/Infrastructure Management & Monitoring | 1
7 | SAP Support | 15+ | SAP Basis & ABAP | 1
8 | Network Services | 5+ | Network & Voice Collaborations | 1
9 | Digital Platforms | Included in App Support | NA | 1
10 | Cyber Security Operations | 15+ | SOC, End-Point Sec, Threat Intell, etc. | 1
Consulting Scope |  | Gap Assessment
Policy & Procedure Optimization
Implementation Consulting
Training & Enablement
Internal Audit & Readiness
Management Review
Certification Support
Project Planning
Preferred start date |  | August end / as early as possible, subject to mobilisation readiness and stakeholder availability.
Available internal resources |  | Yes. Existing PDO IT staff shall cooperate and contribute to implement ISO/IEC 20000-1 requirements, assessments and audits.
Mobilisation prerequisite |  | PDO to confirm service owners, process owners, SME availability, evidence access, workshop calendar and management sponsorship before gap analysis.
Site / travel planning input |  | PDO to confirm site list, access permissions, travel windows and local coordination requirements for implementation, internal audit and certification audit support.
Expected Commercial Model |  | Fixed Price
Milestone Based

## Estimation
PDO ISO/IEC 20000-1 Estimation
Global Inputs
Project Start Date |  | Editable start date
Total Project Duration | 40 Weeks | Overall schedule- 40 Weeks
SME Rate - Oman Resource (OMR/PD) | 200 | Lead Consultant / ISO 20000 SME
Consultant Rate - Oman Resource (OMR/PD) | 125 | Implementation / documentation consultant
Omani Trainee Rate (OMR/PD) | 30 | Assumed rate for two Omani trainees
SME Rate - Indian Resource (OMR/PD) | 100 | Indian Resource
Consultant Rate - Indian Resource (OMR/PD) | 75 | Indian Resource
Travel / Logistics - Oman Resource (OMR) per Resource | 500 | Local logistics placeholder
Travel / Logistics - Indian Resource (OMR) per Resource | 3600 | Room 3000 + Travel 600 as per prior assumption
Domestic To and Fro charge through Air per Travel | 200 | Total 4 Sites. One domestic Air travel will be done and other sites will be connected through road transport.
# of Domestic Air Travels | 2 | Travel to North and South through Air and use Road Transport for reaching other 3 sites.
# of Domestic Trips | 3 | 3 Travels - 1 for implementation, 1 for Internal Audit and 1 External Audit
Total Domestic Travel Expense (Air & Road Transport) | 1200 | Domestic travel expense based on 3 travel cycles. Additive to base travel/logistics in commercial summary.
Domestic Local Road Travel Effort - 8 Sites | 8 | 8 sites x 1 PD local road travel per site = 8 PD. Effort is included in SME effort and costed separately for visibility.
Contingency % | 10% | Applied to consulting costs
Certification Body Cost Placeholder (OMR) |  | PDO Scope
Currency | OMR | Commercial currency
S.No | Service Name | Resource Input | Service Description | Gap Analysis PD | Policy & Procedure PD | Implementation PD | Training PD | Internal Audit PD | Certification Support PD | Total Service PD | Remarks
1 | Infrastructure Services | 15+ | Hosting, Database, Storage, Back-up, AD, etc. | 2 | 4 | 25 | 2 | 2 | 2 | 37 | Service effort as per given input.
2 | End User Support | 50+ | ServiceDesk & Hardware & Asset Management | 5 | 6 | 35 | 5 | 5 | 5 | 61 | Service effort as per given input.
3 | Cloud Services | Scattered across Apps Team | Cloud Hosting coordination services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Zero effort per input; included in Application Support / not separately estimated.
4 | Application Support | 50+ (incl. Contractors) | App Development, testing, run & maintain | 5 | 6 | 35 | 5 | 5 | 5 | 61 | Service effort as per given input.
5 | Field Communication Systems | 10+ | WiMAX & Tetra Services | 2 | 4 | 25 | 2 | 2 | 2 | 37 | Service effort as per given input.
6 | Data Centre | 7+ | Data Center Facilities/Infrastructure Management & Monitoring | 2 | 4 | 25 | 2 | 2 | 2 | 37 | Service effort as per given input.
7 | SAP Support | 15+ | SAP Basis & ABAP | 2 | 4 | 25 | 2 | 2 | 2 | 37 | Service effort as per given input.
8 | Network Services | 5+ | Network & Voice Collaborations | 2 | 4 | 25 | 2 | 2 | 2 | 37 | Service effort as per given input.
9 | Digital Platforms | Included in App Support | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Zero effort per input; included in Application Support / not separately estimated.
10 | Cyber Security Operations | 15+ | SOC, End-Point Sec, Threat Intell, etc. | 2 | 4 | 25 | 2 | 2 | 2 | 37 | Service effort as per given input.
|  |  |  | 22 | 36 | 220 | 22 | 22 | 22 | 344
Program Management Effort
ID | Program Management | Scope | Description | Effort PD | Resource Type
C1 | Project Initiation & Governance | All services | Kick-off, scope confirmation, governance, evidence tracker and schedule planning. | 8 | SME
C2 | Understanding of PDO Ecosystem | All services | Understand PDO organization context, IDD operating model, service landscape, stakeholder structure, technology ecosystem, supplier interfaces, service dependencies and site context before formal gap assessment. | 12 | SME
C3 | PDO Team Commitment and Availability for Gap Analysis | All services | Obtain management and team commitment for gap assessment workshops, confirm PDO SME availability, service owner participation, process owner nominations, evidence owners and workshop calendar. | 12 | SME
C4 | Mobilization and Engagement Readiness | All services | Mobilization covers onboarding, access readiness, evidence request follow-up, questionnaire clarification, detailed schedule finalization, site/audit coordination and readiness for gap analysis. | 22 | SME
C5 | Management Review Facilitation | All services | Management review preparation, facilitation, minutes and action tracking. | 4 | SME
C6 | Project Tracking | All services | Project management, governance tracking, coordination, status reporting, issue/risk follow-up and stakeholder communication. | 69 | SME
C7 | Two Omani Trainees during Implementation | Implementation phase | 2 trainees x 5 PD/week x 25 weeks for implementation assistance and knowledge transfer. | 250 | Omani Trainee
C8 | Domestic Site Travel / Local Road Travel | 8 sites | Local road travel effort for 8 sites at 1 PD per site. Supports site familiarisation, implementation coordination, internal audit readiness and certification preparation logistics. Total 3 Trips | 24 | SME / Travel
Effort Summary
Project Initiation & Governance PD |  |  | 8
Understanding of PDO Ecosystem PD |  |  | 12
PDO Team Commitment and Gap Readiness PD |  |  | 12
Mobilization & Engagement Readiness PD |  |  | 22
Service Management Lifecycle Effort PD |  |  | 344
Management Review PD |  |  | 4
Project Management Activity PD |  |  | 69
Omani Trainee Support PD |  |  | 250
Domestic Site Travel Effort PD |  |  | 24
Total Programme Effort PD |  |  | 745
Commercial Summary
Resource Model | SME Effort PD | Consultant Effort PD | Trainee Effort PD | SME Rate | Consultant Rate | Trainee Rate | Consulting Cost | Base Travel / Logistics | Domestic Travel Expense | Total Program Cost | Total Program Cost with Contigency | 6 Months Maintenance Cost | Total incl. Maintenance | Gross Margin % | Total Program Cost with GM | Total Program Cost Incl. Maintenance with GM
Using Oman Resources + Omani Trainees | 208 | 287 | 250 | 200 | 125 | 30 | 84975 | 2000 | 1200 | 88175 | 96992.5 | 17325 | 116050 | 40% | 135789.5 | 162470
Using Indian Resources + Omani Trainees | 208 | 287 | 250 | 100 | 75 | 30 | 49825 | 14400 | 1200 | 65425 | 71967.5 | 13695 | 87032 | 40% | 100754.5 | 121844.8

## 6 Months Maintenance Plan
PDO ISO/IEC 20000-1 6 Months Maintenance Plan
Post-certification support effort and cost for 6 months
Maintenance Workstream | Owner | Annual Effort PD | Oman Rate | Oman Cost | India/Offshore Rate | India/Offshore Cost | Deliverables | Notes
Maintenance Support (Handing Over and Monitoring) - Offshore | Consultant | 66 | 125 | 8250 | 75 | 4950 | Updated document/evidence tracker and improvement register | Supports continual improvement and audit evidence upkeep Surveillance preparation pack, Handing over and Monitoring
Omani trainee continuity support | 2 Omani Trainees | 250 | 30 | 7500 | 30 | 7500 | Trainee support log, knowledge retention and evidence assistance | Assumes 2 Omani trainees continue support
TOTAL MAINTENANCE COST |  |  |  | 15750 |  | 12450
Contingency @ 10% |  |  |  | 1575 |  | 1245
TOTAL WITH CONTINGENCY |  |  |  | 17325 |  | 13695