## Cover
PDO ISO/IEC 20000-1 Engagement
Program Plan
Program Start Date | 2026-09-16 | (Tentative)
Planning Horizon/ Duration | 40 weeks based on Schedule Summary activity range
Deliverables | - Project Charter - Detailed Schedule - Weekly Summary - Gantt Chart based on Resource Loading - Resource Loading

## Project Charter
Project Charter - PDO ISO/IEC 20000-1 Engagement
Prepared directly from the Resource Loading sheet in this workbook
Charter Element | Description
Project Title | PDO ISO/IEC 20000-1 Certification Engagement
Purpose | Plan, mobilize, assess, optimize, implement, train, audit and support certification readiness for PDO IT service management practices.
Primary Planning Source | Resource Loading sheet in the same workbook
Project Start Date | 2026-09-16
Project End Date | 2027-06-20
Planning Duration | 40 weeks
Total Planned Resource Loading PD | 745
Peak Weekly PD | 30
Peak FTE Equivalent | 6
Key Resource Types | SME/ PM, Senior Consultant, Consultant 1, Consultant 2 and Omani Trainees
Governance Cadence | Weekly project status, RAID/action tracking and steering updates through project management activity.
Success Criteria | Completion of mobilization readiness, gap assessment, optimized documentation, implementation evidence, training, internal audit, management review and certification support.
Project Objectives
Objectives | Establish engagement governance and confirm scope, stakeholders, evidence access and working calendar.
Understand the PDO IDD operating model, service landscape, dependencies and site context before formal gap assessment.
Execute service-wise gap assessment and optimize policies, procedures and evidence maps.
Support implementation consulting, training, internal audit readiness, management review and certification audit response.
Enable knowledge transfer through Omani trainee participation during execution.
Activities | Start Week | End Week | Start Date | End Date | Planned PD
Initiation & Governance | 1 | 2 | 2026-09-16 | 2026-09-27 | 8
Understanding of PDO Ecosystem | 2 | 4 | 2026-09-23 | 2026-10-11 | 12
PDO Team Commitment and Availability for Gap Analysis | 5 | 7 | 2026-10-14 | 2026-11-01 | 12
Mobilization and Engagement Readiness | 7 | 11 | 2026-10-28 | 2026-11-29 | 22
Project Management Activity | 7 | 38 | 2026-10-28 | 2027-06-06 | 69
Gap Assessment | 12 | 17 | 2026-12-02 | 2027-01-10 | 22
Policy & Procedure Optimization | 18 | 25 | 2027-01-13 | 2027-03-07 | 36
Implementation Consulting | 19 | 36 | 2027-01-20 | 2027-05-23 | 220
Domestic Travel | 26 | 40 | 2027-03-10 | 2027-06-20 | 24
Training & Enablement | 27 | 31 | 2027-03-17 | 2027-04-18 | 22
Internal Audit & Readiness | 34 | 37 | 2027-05-05 | 2027-05-30 | 22
Management Review | 38 | 38 | 2027-06-02 | 2027-06-06 | 4
Certification Support | 39 | 40 | 2027-06-09 | 2027-06-20 | 22
Trainee Support | 16 | 40 | 2026-12-30 | 2027-06-20 | 250
Key Assumptions and Risks | Impact / Mitigation
PDO SME availability is confirmed as per planned weeks | Slippage in availability can affect gap assessment, evidence readiness and certification support dates.
Identification of Certification of Certification Body | Delay in Identifiying Certifying Body may impact the project completion timelines.
Resource loading is treated as the controlling planning baseline | Detailed schedule and Gantt are derived from first and last non-zero weekly loading per activity.
Domestic travel/site access is available during planned windows | Travel and site coordination should be locked four weeks before relevant activity windows.
Omani trainees are available throughout the indicated support window | If trainee availability changes, knowledge transfer and evidence support effort should be rebalanced.
RASCI Matrix
Legend | R = Responsible, A = Accountable, S = Support, C = Consulted, I = Informed
Activity / Deliverable | PDO Executive Sponsor | PDO Project Manager | PDO Service Owners | PDO Process Owners | PDO SMEs / Evidence Owners | Engagement Lead / SME | Senior Consultant | Consultant 1 | Consultant 2 | Omani Trainees | Certification Body
Project Initiation & Governance | A | R | C | C | I | R | S | I | I | I | I
Understanding of PDO Ecosystem | I | A | C | C | S | R | S | C | C | I | I
PDO Team Commitment and Workshop Calendar | A | R | C | C | S | R | S | I | I | I | I
Mobilization and Engagement Readiness | I | A | C | C | S | R | S | I | I | I | I
Gap Assessment | I | A | C | C | S | R | S | C | C | I | I
Policy & Procedure Optimization | I | A | C | C | S | A | R | S | S | C | I
Implementation Consulting | I | A | C | C | S | A | R | R | R | S | I
Training & Enablement | I | A | C | C | S | R | S | S | S | S | I
Internal Audit & Readiness | I | A | C | C | S | R | S | C | C | I | I
Management Review | A | R | C | C | C | R | S | I | I | I | I
Certification Support | I | A | C | C | S | R | S | S | S | I | C
Project Management, RAID and Reporting | I | A/R | I | I | I | R | S | I | I | I | I
Domestic Site Travel Coordination | I | A | C | I | S | R | S | S | S | I | I
Omani Trainee Support and Knowledge Transfer | I | A | C | C | S | R | S | S | S | R/S | I
RASCI Interpretation Note | A I A I I I I I I A I I I I: Accountable ownership remains with PDO for decisions, approvals and availability commitments. Consulting resources are responsible/supporting for delivery activities as per the Resource Loading baseline.

## Detailed Schedule
Detailed Schedule - Derived from Resource Loading
Start and end weeks are calculated from the first and last non-zero weekly loading for each activity
ID | Phase | Activity | Service / Scope | Resource Type | Planned PD | Loaded PD | Variance PD | Start Week | End Week | Start Date | End Date | Duration Weeks | Predecessor / Dependency | Key Deliverable | Status / Remarks
1 | Initiation & Governance | Kick-off, scope confirmation, governance, evidence tracker and working calendar | All services | SME | 8 | 8 | 0 | 1 | 2 | 2026-09-16 | 2026-09-27 | 2 | Project approval | Project charter, governance cadence, kickoff pack and evidence tracker | Planned
2 | Understanding of PDO Ecosystem | Understand IDD operating model, service landscape, stakeholders, dependencies, suppliers and site context | All services | SME | 12 | 12 | 0 | 2 | 4 | 2026-09-23 | 2026-10-11 | 3 | Initiation & Governance | PDO IDD ecosystem assessment note, stakeholder map and service landscape summary | Planned
3 | PDO Team Commitment and Availability for Gap Analysis | Confirm service owners, process owners, SME participation, evidence owners and workshop calendar | All services | SME | 12 | 12 | 0 | 5 | 7 | 2026-10-14 | 2026-11-01 | 3 | Understanding of PDO Ecosystem | Confirmed service/process owner availability and gap assessment workshop calendar | Planned
4 | Mobilization and Engagement Readiness | Onboarding, access readiness, evidence request follow-up, questionnaire clarification and site/audit coordination | All services | SME | 22 | 22 | 0 | 7 | 11 | 2026-10-28 | 2026-11-29 | 5 | PDO Team Commitment and Availability for Gap Analysis | Mobilization readiness confirmation, access readiness and evidence request tracker | Planned
5 | Project Management Activity | Governance tracking, status reporting, issues, risks, stakeholder communication and coordination | All services | SME / PM | 69 | 69 | 0 | 7 | 38 | 2026-10-28 | 2027-06-06 | 32 | Ongoing governance | Weekly status report, RAID log, action tracker and steering updates | Planned
6 | Gap Assessment | Gap Assessment - Infrastructure Services | Infrastructure Services | SME | 2 | 2 | 0 | 12 | 12 | 2026-12-02 | 2026-12-06 | 1 | Mobilization and Engagement Readiness | Service-level gap observations, evidence review results and prioritized action list | Planned
7 | Gap Assessment | Gap Assessment - End User Support | End User Support | SME | 8 | 8 | 0 | 13 | 14 | 2026-12-09 | 2026-12-20 | 2 | Mobilization and Engagement Readiness | Service-level gap observations, evidence review results and prioritized action list | Planned
8 | Gap Assessment | Gap Assessment - Application Support | Application Support | SME | 2 | 2 | 0 | 15 | 15 | 2026-12-23 | 2026-12-27 | 1 | Mobilization and Engagement Readiness | Service-level gap observations, evidence review results and prioritized action list | Planned
9 | Gap Assessment | Gap Assessment - Field Communication Systems | Field Communication Systems | SME | 2 | 2 | 0 | 15 | 15 | 2026-12-23 | 2026-12-27 | 1 | Mobilization and Engagement Readiness | Service-level gap observations, evidence review results and prioritized action list | Planned
10 | Gap Assessment | Gap Assessment - Data Centre | Data Centre | SME | 2 | 2 | 0 | 16 | 16 | 2026-12-30 | 2027-01-03 | 1 | Mobilization and Engagement Readiness | Service-level gap observations, evidence review results and prioritized action list | Planned
11 | Gap Assessment | Gap Assessment - SAP Support | SAP Support | SME | 2 | 2 | 0 | 16 | 16 | 2026-12-30 | 2027-01-03 | 1 | Mobilization and Engagement Readiness | Service-level gap observations, evidence review results and prioritized action list | Planned
12 | Gap Assessment | Gap Assessment - Network Services | Network Services | SME | 2 | 2 | 0 | 17 | 17 | 2027-01-06 | 2027-01-10 | 1 | Mobilization and Engagement Readiness | Service-level gap observations, evidence review results and prioritized action list | Planned
13 | Gap Assessment | Gap Assessment - Cyber Security Operations | Cyber Security Operations | SME | 2 | 2 | 0 | 17 | 17 | 2027-01-06 | 2027-01-10 | 1 | Mobilization and Engagement Readiness | Service-level gap observations, evidence review results and prioritized action list | Planned
14 | Policy & Procedure Optimization | Policy & Procedure Optimization - Infrastructure Services | Infrastructure Services | Sr Consultant | 4 | 4 | 0 | 18 | 18 | 2027-01-13 | 2027-01-17 | 1 | Gap Assessment outputs | Optimized policies, procedures, process maps and evidence mapping | Planned
15 | Policy & Procedure Optimization | Policy & Procedure Optimization - End User Support | End User Support | Sr Consultant | 8 | 8 | 0 | 18 | 20 | 2027-01-13 | 2027-01-31 | 3 | Gap Assessment outputs | Optimized policies, procedures, process maps and evidence mapping | Planned
16 | Policy & Procedure Optimization | Policy & Procedure Optimization - Application Support | Application Support | Sr Consultant | 4 | 4 | 0 | 20 | 20 | 2027-01-27 | 2027-01-31 | 1 | Gap Assessment outputs | Optimized policies, procedures, process maps and evidence mapping | Planned
17 | Policy & Procedure Optimization | Policy & Procedure Optimization - Field Communication Systems | Field Communication Systems | Sr Consultant | 4 | 4 | 0 | 21 | 21 | 2027-02-03 | 2027-02-07 | 1 | Gap Assessment outputs | Optimized policies, procedures, process maps and evidence mapping | Planned
18 | Policy & Procedure Optimization | Policy & Procedure Optimization - Data Centre | Data Centre | Sr Consultant | 4 | 4 | 0 | 22 | 22 | 2027-02-10 | 2027-02-14 | 1 | Gap Assessment outputs | Optimized policies, procedures, process maps and evidence mapping | Planned
19 | Policy & Procedure Optimization | Policy & Procedure Optimization - SAP Support | SAP Support | Sr Consultant | 4 | 4 | 0 | 23 | 23 | 2027-02-17 | 2027-02-21 | 1 | Gap Assessment outputs | Optimized policies, procedures, process maps and evidence mapping | Planned
20 | Policy & Procedure Optimization | Policy & Procedure Optimization - Network Services | Network Services | Sr Consultant | 4 | 4 | 0 | 24 | 24 | 2027-02-24 | 2027-02-28 | 1 | Gap Assessment outputs | Optimized policies, procedures, process maps and evidence mapping | Planned
21 | Policy & Procedure Optimization | Policy & Procedure Optimization - Cyber Security Operations | Cyber Security Operations | Sr Consultant | 4 | 4 | 0 | 25 | 25 | 2027-03-03 | 2027-03-07 | 1 | Gap Assessment outputs | Optimized policies, procedures, process maps and evidence mapping | Planned
22 | Implementation Consulting | Implementation Consulting - Infrastructure Services | Infrastructure Services | Sr Consultant | 21 | 21 | 0 | 21 | 29 | 2027-02-03 | 2027-04-04 | 9 | Approved optimized documents and gap action plan | Implemented service management practices, evidence records and operationalised controls | Planned
23 | Domestic Travel | Domestic Travel for Implementation- 4 Sites North | All services | Sr Consultant | 4 | 4 | 0 | 26 | 29 | 2027-03-10 | 2027-04-04 | 4 | Confirmed site access and travel calendar | Site visit coordination log, travel evidence and site support notes | Planned
24 | Implementation Consulting | Implementation Consulting | All services | Sr Consultant | 29 | 29 | 0 | 30 | 36 | 2027-04-07 | 2027-05-23 | 7 | Approved optimized documents and gap action plan | Implemented service management practices, evidence records and operationalised controls | Planned
25 | Domestic Travel | Domestic Travel for Implementation- 4 Sites South | All services | Sr Consultant | 4 | 4 | 0 | 30 | 33 | 2027-04-07 | 2027-05-02 | 4 | Confirmed site access and travel calendar | Site visit coordination log, travel evidence and site support notes | Planned
26 | Implementation Consulting | Implementation Consulting - End User Support | End User Support | Consultant 1 | 35 | 35 | 0 | 19 | 25 | 2027-01-20 | 2027-03-07 | 7 | Approved optimized documents and gap action plan | Implemented service management practices, evidence records and operationalised controls | Planned
27 | Implementation Consulting | Implementation Consulting - Application Support | Application Support | Consultant 1 | 35 | 35 | 0 | 26 | 32 | 2027-03-10 | 2027-04-25 | 7 | Approved optimized documents and gap action plan | Implemented service management practices, evidence records and operationalised controls | Planned
28 | Implementation Consulting | Implementation Consulting - Field Communication Systems | Field Communication Systems | Consultant 1 | 15 | 15 | 0 | 33 | 35 | 2027-04-28 | 2027-05-16 | 3 | Approved optimized documents and gap action plan | Implemented service management practices, evidence records and operationalised controls | Planned
29 | Implementation Consulting | Implementation Consulting - Data Centre | Data Centre | Consultant 2 | 25 | 25 | 0 | 19 | 23 | 2027-01-20 | 2027-02-21 | 5 | Approved optimized documents and gap action plan | Implemented service management practices, evidence records and operationalised controls | Planned
30 | Implementation Consulting | Implementation Consulting - SAP Support | SAP Support | Consultant 2 | 25 | 25 | 0 | 24 | 28 | 2027-02-24 | 2027-03-28 | 5 | Approved optimized documents and gap action plan | Implemented service management practices, evidence records and operationalised controls | Planned
31 | Implementation Consulting | Implementation Consulting - Network Services | Network Services | Consultant 2 | 25 | 25 | 0 | 29 | 33 | 2027-03-31 | 2027-05-02 | 5 | Approved optimized documents and gap action plan | Implemented service management practices, evidence records and operationalised controls | Planned
32 | Implementation Consulting | Implementation Consulting - Cyber Security Operations | Cyber Security Operations | Consultant 2 | 10 | 10 | 0 | 34 | 35 | 2027-05-05 | 2027-05-16 | 2 | Approved optimized documents and gap action plan | Implemented service management practices, evidence records and operationalised controls | Planned
33 | Training & Enablement | Training & Enablement - Infrastructure Services | Infrastructure Services | SME | 2 | 2 | 0 | 27 | 27 | 2027-03-17 | 2027-03-21 | 1 | Policy / process availability and implementation readiness | Awareness sessions, process owner enablement and attendance records | Planned
34 | Training & Enablement | Training & Enablement - End User Support | End User Support | SME | 5 | 5 | 0 | 29 | 29 | 2027-03-31 | 2027-04-04 | 1 | Policy / process availability and implementation readiness | Awareness sessions, process owner enablement and attendance records | Planned
35 | Training & Enablement | Training & Enablement - Application Support | Application Support | SME | 5 | 5 | 0 | 30 | 30 | 2027-04-07 | 2027-04-11 | 1 | Policy / process availability and implementation readiness | Awareness sessions, process owner enablement and attendance records | Planned
36 | Training & Enablement | Training & Enablement - Field Communication Systems | Field Communication Systems | SME | 2 | 2 | 0 | 27 | 27 | 2027-03-17 | 2027-03-21 | 1 | Policy / process availability and implementation readiness | Awareness sessions, process owner enablement and attendance records | Planned
37 | Training & Enablement | Training & Enablement - Data Centre | Data Centre | SME | 2 | 2 | 0 | 27 | 28 | 2027-03-17 | 2027-03-28 | 2 | Policy / process availability and implementation readiness | Awareness sessions, process owner enablement and attendance records | Planned
38 | Training & Enablement | Training & Enablement - SAP Support | SAP Support | SME | 2 | 2 | 0 | 28 | 28 | 2027-03-24 | 2027-03-28 | 1 | Policy / process availability and implementation readiness | Awareness sessions, process owner enablement and attendance records | Planned
39 | Training & Enablement | Training & Enablement - Network Services | Network Services | SME | 2 | 2 | 0 | 28 | 28 | 2027-03-24 | 2027-03-28 | 1 | Policy / process availability and implementation readiness | Awareness sessions, process owner enablement and attendance records | Planned
40 | Training & Enablement | Training & Enablement - Cyber Security Operations | Cyber Security Operations | SME | 2 | 2 | 0 | 31 | 31 | 2027-04-14 | 2027-04-18 | 1 | Policy / process availability and implementation readiness | Awareness sessions, process owner enablement and attendance records | Planned
41 | Internal Audit & Readiness | Internal Audit & Readiness - Infrastructure Services | Infrastructure Services | SME | 2 | 2 | 0 | 34 | 34 | 2027-05-05 | 2027-05-09 | 1 | Implementation evidence readiness | Internal audit report, readiness assessment and corrective action tracker | Planned
42 | Internal Audit & Readiness | Internal Audit & Readiness - End User Support | End User Support | SME | 5 | 5 | 0 | 36 | 37 | 2027-05-19 | 2027-05-30 | 2 | Implementation evidence readiness | Internal audit report, readiness assessment and corrective action tracker | Planned
43 | Domestic Travel | Domestic Travel for Internal Audit- 4 Sites North | All services | SME | 4 | 4 | 0 | 36 | 37 | 2027-05-19 | 2027-05-30 | 2 | Confirmed site access and travel calendar | Site visit coordination log, travel evidence and site support notes | Planned
44 | Internal Audit & Readiness | Internal Audit & Readiness - Application Support | Application Support | SME | 5 | 5 | 0 | 36 | 37 | 2027-05-19 | 2027-05-30 | 2 | Implementation evidence readiness | Internal audit report, readiness assessment and corrective action tracker | Planned
45 | Domestic Travel | Domestic Travel for Implementation- 4 Sites South | All services | SME | 4 | 4 | 0 | 36 | 37 | 2027-05-19 | 2027-05-30 | 2 | Confirmed site access and travel calendar | Site visit coordination log, travel evidence and site support notes | Planned
46 | Internal Audit & Readiness | Internal Audit & Readiness - Field Communication Systems | Field Communication Systems | SME | 2 | 2 | 0 | 34 | 34 | 2027-05-05 | 2027-05-09 | 1 | Implementation evidence readiness | Internal audit report, readiness assessment and corrective action tracker | Planned
47 | Internal Audit & Readiness | Internal Audit & Readiness - Data Centre | Data Centre | SME | 2 | 2 | 0 | 34 | 35 | 2027-05-05 | 2027-05-16 | 2 | Implementation evidence readiness | Internal audit report, readiness assessment and corrective action tracker | Planned
48 | Internal Audit & Readiness | Internal Audit & Readiness - SAP Support | SAP Support | SME | 2 | 2 | 0 | 35 | 35 | 2027-05-12 | 2027-05-16 | 1 | Implementation evidence readiness | Internal audit report, readiness assessment and corrective action tracker | Planned
49 | Internal Audit & Readiness | Internal Audit & Readiness - Network Services | Network Services | SME | 2 | 2 | 0 | 35 | 35 | 2027-05-12 | 2027-05-16 | 1 | Implementation evidence readiness | Internal audit report, readiness assessment and corrective action tracker | Planned
50 | Internal Audit & Readiness | Internal Audit & Readiness - Cyber Security Operations | Cyber Security Operations | Sr Consultant | 2 | 2 | 0 | 37 | 37 | 2027-05-26 | 2027-05-30 | 1 | Implementation evidence readiness | Internal audit report, readiness assessment and corrective action tracker | Planned
51 | Management Review | Management Review | All services | SME | 4 | 4 | 0 | 38 | 38 | 2027-06-02 | 2027-06-06 | 1 | Internal Audit & Readiness | Management review pack, minutes and management action tracker | Planned
52 | Certification Support | Certification Support - Infrastructure Services | Infrastructure Services | Consultant 1 | 2 | 2 | 0 | 39 | 39 | 2027-06-09 | 2027-06-13 | 1 | Management Review and readiness closure | Certification audit support pack, auditor response log and closure evidence | Planned
53 | Certification Support | Certification Support - End User Support | End User Support | Sr Consultant | 5 | 5 | 0 | 39 | 40 | 2027-06-09 | 2027-06-20 | 2 | Management Review and readiness closure | Certification audit support pack, auditor response log and closure evidence | Planned
54 | Domestic Travel | Domestic Travel for Certification Support- 4 Sites North | All services | Sr Consultant | 4 | 4 | 0 | 39 | 40 | 2027-06-09 | 2027-06-20 | 2 | Confirmed site access and travel calendar | Site visit coordination log, travel evidence and site support notes | Planned
55 | Certification Support | Certification Support - Application Support | Application Support | SME | 5 | 5 | 0 | 39 | 40 | 2027-06-09 | 2027-06-20 | 2 | Management Review and readiness closure | Certification audit support pack, auditor response log and closure evidence | Planned
56 | Domestic Travel | Domestic Travel for Certification Support- 4 Sites North | All services | SME | 4 | 4 | 0 | 39 | 40 | 2027-06-09 | 2027-06-20 | 2 | Confirmed site access and travel calendar | Site visit coordination log, travel evidence and site support notes | Planned
57 | Certification Support | Certification Support - Field Communication Systems | Field Communication Systems | Consultant 1 | 2 | 2 | 0 | 39 | 39 | 2027-06-09 | 2027-06-13 | 1 | Management Review and readiness closure | Certification audit support pack, auditor response log and closure evidence | Planned
58 | Certification Support | Certification Support - Data Centre | Data Centre | Consultant 1 | 2 | 2 | 0 | 40 | 40 | 2027-06-16 | 2027-06-20 | 1 | Management Review and readiness closure | Certification audit support pack, auditor response log and closure evidence | Planned
59 | Certification Support | Certification Support - SAP Support | SAP Support | Consultant 1 | 2 | 2 | 0 | 40 | 40 | 2027-06-16 | 2027-06-20 | 1 | Management Review and readiness closure | Certification audit support pack, auditor response log and closure evidence | Planned
60 | Certification Support | Certification Support - Network Services | Network Services | Consultant 1 | 2 | 2 | 0 | 39 | 40 | 2027-06-09 | 2027-06-20 | 2 | Management Review and readiness closure | Certification audit support pack, auditor response log and closure evidence | Planned
61 | Certification Support | Certification Support - Cyber Security Operations | Cyber Security Operations | Consultant 1 | 2 | 2 | 0 | 40 | 40 | 2027-06-16 | 2027-06-20 | 1 | Management Review and readiness closure | Certification audit support pack, auditor response log and closure evidence | Planned
62 | Trainee Support | Omani Trainee 1 | All services | Trainee | 125 | 125 | 0 | 16 | 40 | 2026-12-30 | 2027-06-20 | 25 | Mobilization and trainee onboarding | Trainee activity log, knowledge transfer records and evidence support output | Planned
63 | Trainee Support | Omani Trainee 2 | All services | Trainee | 125 | 125 | 0 | 16 | 40 | 2026-12-30 | 2027-06-20 | 25 | Mobilization and trainee onboarding | Trainee activity log, knowledge transfer records and evidence support output | Planned

## Weekly Summary
Weekly Summary and Resource Loading Profile
Weekly totals derived from the Resource Loading sheet
Week | Week Start | Week End | SME PD | Consultant PD | Trainee PD | Travel PD | Total PD | Total FTE | Key Active Activities
1 | 2026-09-16 | 2026-09-20 | 5 | 0 | 0 | 0 | 5 | 1 | Initiation & Governance
2 | 2026-09-21 | 2026-09-25 | 5 | 0 | 0 | 0 | 5 | 1 | Initiation & Governance; Understanding of PDO Ecosystem
3 | 2026-09-28 | 2026-10-02 | 5 | 0 | 0 | 0 | 5 | 1 | Understanding of PDO Ecosystem
4 | 2026-10-05 | 2026-10-09 | 5 | 0 | 0 | 0 | 5 | 1 | Understanding of PDO Ecosystem
5 | 2026-10-12 | 2026-10-16 | 5 | 0 | 0 | 0 | 5 | 1 | PDO Team Commitment and Availability for Gap Analysis
6 | 2026-10-19 | 2026-10-23 | 5 | 0 | 0 | 0 | 5 | 1 | PDO Team Commitment and Availability for Gap Analysis
7 | 2026-10-26 | 2026-10-30 | 5 | 0 | 0 | 0 | 5 | 1 | PDO Team Commitment and Availability for Gap Analysis; Mobilization and Engagement Readiness; Project Management Activity
8 | 2026-11-02 | 2026-11-06 | 5 | 0 | 0 | 0 | 5 | 1 | Mobilization and Engagement Readiness
9 | 2026-11-09 | 2026-11-13 | 5 | 0 | 0 | 0 | 5 | 1 | Mobilization and Engagement Readiness
10 | 2026-11-16 | 2026-11-20 | 5 | 0 | 0 | 0 | 5 | 1 | Mobilization and Engagement Readiness
11 | 2026-11-23 | 2026-11-27 | 5 | 0 | 0 | 0 | 5 | 1 | Mobilization and Engagement Readiness
12 | 2026-11-30 | 2026-12-04 | 5 | 0 | 0 | 0 | 5 | 1 | Project Management Activity; Gap Assessment
13 | 2026-12-07 | 2026-12-11 | 5 | 0 | 0 | 0 | 5 | 1 | Gap Assessment
14 | 2026-12-14 | 2026-12-18 | 5 | 0 | 0 | 0 | 5 | 1 | Project Management Activity; Gap Assessment
15 | 2026-12-21 | 2026-12-25 | 5 | 0 | 0 | 0 | 5 | 1 | Project Management Activity; Gap Assessment
16 | 2026-12-28 | 2027-01-01 | 5 | 0 | 10 | 0 | 15 | 3 | Project Management Activity; Gap Assessment; Trainee Support
17 | 2027-01-04 | 2027-01-08 | 5 | 0 | 10 | 0 | 15 | 3 | Project Management Activity; Gap Assessment; Trainee Support
18 | 2027-01-11 | 2027-01-15 | 5 | 5 | 10 | 0 | 20 | 4 | Project Management Activity; Policy & Procedure Optimization; Trainee Support
19 | 2027-01-18 | 2027-01-22 | 5 | 15 | 10 | 0 | 30 | 6 | Project Management Activity; Policy & Procedure Optimization; Implementation Consulting; Trainee Support
20 | 2027-01-25 | 2027-01-29 | 5 | 15 | 10 | 0 | 30 | 6 | Project Management Activity; Policy & Procedure Optimization; Implementation Consulting; Trainee Support
21 | 2027-02-01 | 2027-02-05 | 5 | 15 | 10 | 0 | 30 | 6 | Project Management Activity; Policy & Procedure Optimization; Implementation Consulting; Trainee Support
22 | 2027-02-08 | 2027-02-12 | 5 | 15 | 10 | 0 | 30 | 6 | Project Management Activity; Policy & Procedure Optimization; Implementation Consulting; Trainee Support
23 | 2027-02-15 | 2027-02-19 | 5 | 15 | 10 | 0 | 30 | 6 | Project Management Activity; Policy & Procedure Optimization; Implementation Consulting; Trainee Support
24 | 2027-02-22 | 2027-02-26 | 5 | 15 | 10 | 0 | 30 | 6 | Project Management Activity; Policy & Procedure Optimization; Implementation Consulting; Trainee Support
25 | 2027-03-01 | 2027-03-05 | 5 | 15 | 10 | 0 | 30 | 6 | Project Management Activity; Policy & Procedure Optimization; Implementation Consulting; Trainee Support
26 | 2027-03-08 | 2027-03-12 | 5 | 14 | 10 | 1 | 30 | 6 | Project Management Activity; Implementation Consulting; Domestic Travel; Trainee Support
27 | 2027-03-15 | 2027-03-19 | 5 | 14 | 10 | 1 | 30 | 6 | Implementation Consulting; Domestic Travel; Training & Enablement; Trainee Support
28 | 2027-03-22 | 2027-03-26 | 5 | 14 | 10 | 1 | 30 | 6 | Implementation Consulting; Domestic Travel; Training & Enablement; Trainee Support
29 | 2027-03-29 | 2027-04-02 | 5 | 14 | 10 | 1 | 30 | 6 | Implementation Consulting; Domestic Travel; Training & Enablement; Trainee Support
30 | 2027-04-05 | 2027-04-09 | 5 | 14 | 10 | 1 | 30 | 6 | Implementation Consulting; Domestic Travel; Training & Enablement; Trainee Support
31 | 2027-04-12 | 2027-04-16 | 5 | 14 | 10 | 1 | 30 | 6 | Project Management Activity; Implementation Consulting; Domestic Travel; Training & Enablement; Trainee Support
32 | 2027-04-19 | 2027-04-23 | 5 | 14 | 10 | 1 | 30 | 6 | Project Management Activity; Implementation Consulting; Domestic Travel; Trainee Support
33 | 2027-04-26 | 2027-04-30 | 5 | 14 | 10 | 1 | 30 | 6 | Project Management Activity; Implementation Consulting; Domestic Travel; Trainee Support
34 | 2027-05-03 | 2027-05-07 | 5 | 15 | 10 | 0 | 30 | 6 | Implementation Consulting; Internal Audit & Readiness; Trainee Support
35 | 2027-05-10 | 2027-05-14 | 5 | 15 | 10 | 0 | 30 | 6 | Implementation Consulting; Internal Audit & Readiness; Trainee Support
36 | 2027-05-17 | 2027-05-21 | 6 | 3 | 10 | 4 | 23 | 4.6 | Implementation Consulting; Internal Audit & Readiness; Domestic Travel; Trainee Support
37 | 2027-05-24 | 2027-05-28 | 5 | 3 | 10 | 4 | 22 | 4.4 | Project Management Activity; Internal Audit & Readiness; Domestic Travel; Trainee Support
38 | 2027-05-31 | 2027-06-04 | 5 | 0 | 10 | 0 | 15 | 3 | Project Management Activity; Management Review; Trainee Support
39 | 2027-06-07 | 2027-06-11 | 3 | 8 | 10 | 4 | 25 | 5 | Certification Support; Domestic Travel; Trainee Support
40 | 2027-06-14 | 2027-06-18 | 2 | 9 | 10 | 4 | 25 | 5 | Certification Support; Domestic Travel; Trainee Support
[7 empty] | 745 | 149

## Gantt Chart
Gantt Chart - Derived from Resource Loading
Bars represent active weeks from the weekly resource loading baseline
ID | Phase | Activity | Resource Type | Planned PD | Start Week | End Week | W1 16-Sep | W2 23-Sep | W3 30-Sep | W4 07-Oct | W5 14-Oct | W6 21-Oct | W7 28-Oct | W8 04-Nov | W9 11-Nov | W10 18-Nov | W11 25-Nov | W12 02-Dec | W13 09-Dec | W14 16-Dec | W15 23-Dec | W16 30-Dec | W17 06-Jan | W18 13-Jan | W19 20-Jan | W20 27-Jan | W21 03-Feb | W22 10-Feb | W23 17-Feb | W24 24-Feb | W25 03-Mar | W26 10-Mar | W27 17-Mar | W28 24-Mar | W29 31-Mar | W30 07-Apr | W31 14-Apr | W32 21-Apr | W33 28-Apr | W34 05-May | W35 12-May | W36 19-May | W37 26-May | W38 02-Jun | W39 09-Jun | W40 16-Jun
1 | Initiation & Governance | Kick-off, scope confirmation, governance, evidence tracker and working calendar | SME | 8 | 1 | 2 | 5 | 3
2 | Understanding of PDO Ecosystem | Understand IDD operating model, service landscape, stakeholders, dependencies, suppliers and site context | SME | 12 | 2 | 4 |  | 2 | 5 | 5
3 | PDO Team Commitment and Availability for Gap Analysis | Confirm service owners, process owners, SME participation, evidence owners and workshop calendar | SME | 12 | 5 | 7 |  |  |  |  | 5 | 5 | 2
4 | Mobilization and Engagement Readiness | Onboarding, access readiness, evidence request follow-up, questionnaire clarification and site/audit coordination | SME | 22 | 7 | 11 | [6 empty] | 2 | 5 | 5 | 5 | 5
5 | Project Management Activity | Governance tracking, status reporting, issues, risks, stakeholder communication and coordination | SME / PM | 69 | 7 | 38 | [6 empty] | 1 |  |  |  |  | 3 |  | 2 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 3 | 5 | 5 |  |  |  | 1 | 1
6 | Gap Assessment | Gap Assessment - Infrastructure Services | SME | 2 | 12 | 12 | [11 empty] | 2
7 | Gap Assessment | Gap Assessment - End User Support | SME | 8 | 13 | 14 | [12 empty] | 5 | 3
8 | Gap Assessment | Gap Assessment - Application Support | SME | 2 | 15 | 15 | [14 empty] | 2
9 | Gap Assessment | Gap Assessment - Field Communication Systems | SME | 2 | 15 | 15 | [14 empty] | 2
10 | Gap Assessment | Gap Assessment - Data Centre | SME | 2 | 16 | 16 | [15 empty] | 2
11 | Gap Assessment | Gap Assessment - SAP Support | SME | 2 | 16 | 16 | [15 empty] | 2
12 | Gap Assessment | Gap Assessment - Network Services | SME | 2 | 17 | 17 | [16 empty] | 2
13 | Gap Assessment | Gap Assessment - Cyber Security Operations | SME | 2 | 17 | 17 | [16 empty] | 2
14 | Policy & Procedure Optimization | Policy & Procedure Optimization - Infrastructure Services | Sr Consultant | 4 | 18 | 18 | [17 empty] | 4
15 | Policy & Procedure Optimization | Policy & Procedure Optimization - End User Support | Sr Consultant | 8 | 18 | 20 | [17 empty] | 1 | 5 | 2
16 | Policy & Procedure Optimization | Policy & Procedure Optimization - Application Support | Sr Consultant | 4 | 20 | 20 | [19 empty] | 4
17 | Policy & Procedure Optimization | Policy & Procedure Optimization - Field Communication Systems | Sr Consultant | 4 | 21 | 21 | [20 empty] | 4
18 | Policy & Procedure Optimization | Policy & Procedure Optimization - Data Centre | Sr Consultant | 4 | 22 | 22 | [21 empty] | 4
19 | Policy & Procedure Optimization | Policy & Procedure Optimization - SAP Support | Sr Consultant | 4 | 23 | 23 | [22 empty] | 4
20 | Policy & Procedure Optimization | Policy & Procedure Optimization - Network Services | Sr Consultant | 4 | 24 | 24 | [23 empty] | 4
21 | Policy & Procedure Optimization | Policy & Procedure Optimization - Cyber Security Operations | Sr Consultant | 4 | 25 | 25 | [24 empty] | 4
22 | Implementation Consulting | Implementation Consulting - Infrastructure Services | Sr Consultant | 21 | 21 | 29 | [20 empty] | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 4 | 4
23 | Domestic Travel | Domestic Travel for Implementation- 4 Sites North | Sr Consultant | 4 | 26 | 29 | [25 empty] | 1 | 1 | 1 | 1
24 | Implementation Consulting | Implementation Consulting | Sr Consultant | 29 | 30 | 36 | [29 empty] | 4 | 4 | 4 | 4 | 5 | 5 | 3
25 | Domestic Travel | Domestic Travel for Implementation- 4 Sites South | Sr Consultant | 4 | 30 | 33 | [29 empty] | 1 | 1 | 1 | 1
26 | Implementation Consulting | Implementation Consulting - End User Support | Consultant 1 | 35 | 19 | 25 | [18 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5
27 | Implementation Consulting | Implementation Consulting - Application Support | Consultant 1 | 35 | 26 | 32 | [25 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5
28 | Implementation Consulting | Implementation Consulting - Field Communication Systems | Consultant 1 | 15 | 33 | 35 | [32 empty] | 5 | 5 | 5
29 | Implementation Consulting | Implementation Consulting - Data Centre | Consultant 2 | 25 | 19 | 23 | [18 empty] | 5 | 5 | 5 | 5 | 5
30 | Implementation Consulting | Implementation Consulting - SAP Support | Consultant 2 | 25 | 24 | 28 | [23 empty] | 5 | 5 | 5 | 5 | 5
31 | Implementation Consulting | Implementation Consulting - Network Services | Consultant 2 | 25 | 29 | 33 | [28 empty] | 5 | 5 | 5 | 5 | 5
32 | Implementation Consulting | Implementation Consulting - Cyber Security Operations | Consultant 2 | 10 | 34 | 35 | [33 empty] | 5 | 5
33 | Training & Enablement | Training & Enablement - Infrastructure Services | SME | 2 | 27 | 27 | [26 empty] | 2
34 | Training & Enablement | Training & Enablement - End User Support | SME | 5 | 29 | 29 | [28 empty] | 5
35 | Training & Enablement | Training & Enablement - Application Support | SME | 5 | 30 | 30 | [29 empty] | 5
36 | Training & Enablement | Training & Enablement - Field Communication Systems | SME | 2 | 27 | 27 | [26 empty] | 2
37 | Training & Enablement | Training & Enablement - Data Centre | SME | 2 | 27 | 28 | [26 empty] | 1 | 1
38 | Training & Enablement | Training & Enablement - SAP Support | SME | 2 | 28 | 28 | [27 empty] | 2
39 | Training & Enablement | Training & Enablement - Network Services | SME | 2 | 28 | 28 | [27 empty] | 2
40 | Training & Enablement | Training & Enablement - Cyber Security Operations | SME | 2 | 31 | 31 | [30 empty] | 2
41 | Internal Audit & Readiness | Internal Audit & Readiness - Infrastructure Services | SME | 2 | 34 | 34 | [33 empty] | 2
42 | Internal Audit & Readiness | Internal Audit & Readiness - End User Support | SME | 5 | 36 | 37 | [35 empty] | 3 | 2
43 | Domestic Travel | Domestic Travel for Internal Audit- 4 Sites North | SME | 4 | 36 | 37 | [35 empty] | 2 | 2
44 | Internal Audit & Readiness | Internal Audit & Readiness - Application Support | SME | 5 | 36 | 37 | [35 empty] | 3 | 2
45 | Domestic Travel | Domestic Travel for Implementation- 4 Sites South | SME | 4 | 36 | 37 | [35 empty] | 2 | 2
46 | Internal Audit & Readiness | Internal Audit & Readiness - Field Communication Systems | SME | 2 | 34 | 34 | [33 empty] | 2
47 | Internal Audit & Readiness | Internal Audit & Readiness - Data Centre | SME | 2 | 34 | 35 | [33 empty] | 1 | 1
48 | Internal Audit & Readiness | Internal Audit & Readiness - SAP Support | SME | 2 | 35 | 35 | [34 empty] | 2
49 | Internal Audit & Readiness | Internal Audit & Readiness - Network Services | SME | 2 | 35 | 35 | [34 empty] | 2
50 | Internal Audit & Readiness | Internal Audit & Readiness - Cyber Security Operations | Sr Consultant | 2 | 37 | 37 | [36 empty] | 2
51 | Management Review | Management Review | SME | 4 | 38 | 38 | [37 empty] | 4
52 | Certification Support | Certification Support - Infrastructure Services | Consultant 1 | 2 | 39 | 39 | [38 empty] | 2
53 | Certification Support | Certification Support - End User Support | Sr Consultant | 5 | 39 | 40 | [38 empty] | 3 | 2
54 | Domestic Travel | Domestic Travel for Certification Support- 4 Sites North | Sr Consultant | 4 | 39 | 40 | [38 empty] | 2 | 2
55 | Certification Support | Certification Support - Application Support | SME | 5 | 39 | 40 | [38 empty] | 3 | 2
56 | Domestic Travel | Domestic Travel for Certification Support- 4 Sites North | SME | 4 | 39 | 40 | [38 empty] | 2 | 2
57 | Certification Support | Certification Support - Field Communication Systems | Consultant 1 | 2 | 39 | 39 | [38 empty] | 2
58 | Certification Support | Certification Support - Data Centre | Consultant 1 | 2 | 40 | 40 | [39 empty] | 2
59 | Certification Support | Certification Support - SAP Support | Consultant 1 | 2 | 40 | 40 | [39 empty] | 2
60 | Certification Support | Certification Support - Network Services | Consultant 1 | 2 | 39 | 40 | [38 empty] | 1 | 1
61 | Certification Support | Certification Support - Cyber Security Operations | Consultant 1 | 2 | 40 | 40 | [39 empty] | 2
62 | Trainee Support | Omani Trainee 1 | Trainee | 125 | 16 | 40 | [15 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
63 | Trainee Support | Omani Trainee 2 | Trainee | 125 | 16 | 40 | [15 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
745

## Resource Loading
Role / Activity | Source Phase | Resource Type | Total Planned PD | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40
Kick-off, scope confirmation, governance, evidence tracker and working calendar | Initiation & Governance | SME | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Understand IDD operating model, service landscape, stakeholders, dependencies, suppliers and site context | Understanding of PDO Ecosystem | SME | 12 | 0 | 2 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Confirm service owners, process owners, SME participation, evidence owners and workshop calendar | PDO Team Commitment and Availability for Gap Analysis | SME | 12 | 0 | 0 | 0 | 0 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onboarding, access readiness, evidence request follow-up, questionnaire clarification and site/audit coordination | Mobilization and Engagement Readiness | SME | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Governance tracking, status reporting, issues, risks, stakeholder communication and coordination | Project Management Activity | SME / PM | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 2 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 5 | 5 | 0 | 0 | 0 | 1 | 1 | 0 | 0
Gap Assessment - Infrastructure Services | Gap Assessment | SME | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gap Assessment - End User Support | Gap Assessment | SME | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gap Assessment - Application Support | Gap Assessment | SME | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gap Assessment - Field Communication Systems | Gap Assessment | SME | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gap Assessment - Data Centre | Gap Assessment | SME | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gap Assessment - SAP Support | Gap Assessment | SME | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gap Assessment - Network Services | Gap Assessment | SME | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gap Assessment - Cyber Security Operations | Gap Assessment | SME | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Policy & Procedure Optimization - Infrastructure Services | Policy & Procedure Optimization | Sr Consultant | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Policy & Procedure Optimization - End User Support | Policy & Procedure Optimization | Sr Consultant | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Policy & Procedure Optimization - Application Support | Policy & Procedure Optimization | Sr Consultant | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Policy & Procedure Optimization - Field Communication Systems | Policy & Procedure Optimization | Sr Consultant | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Policy & Procedure Optimization - Data Centre | Policy & Procedure Optimization | Sr Consultant | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Policy & Procedure Optimization - SAP Support | Policy & Procedure Optimization | Sr Consultant | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Policy & Procedure Optimization - Network Services | Policy & Procedure Optimization | Sr Consultant | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Policy & Procedure Optimization - Cyber Security Operations | Policy & Procedure Optimization | Sr Consultant | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Implementation Consulting - Infrastructure Services | Implementation Consulting | Sr Consultant | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Domestic Travel for Implementation- 4 Sites North | Sr Consultant | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
| Implementation Consulting | Sr Consultant | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 5 | 5 | 3 |  | 0 | 0 | 0
| Domestic Travel for Implementation- 4 Sites South | Sr Consultant | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
Implementation Consulting - End User Support | Implementation Consulting | Consultant 1 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implementation Consulting - Application Support | Implementation Consulting | Consultant 1 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implementation Consulting - Field Communication Systems | Implementation Consulting | Consultant 1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0
Implementation Consulting - Data Centre | Implementation Consulting | Consultant 2 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implementation Consulting - SAP Support | Implementation Consulting | Consultant 2 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implementation Consulting - Network Services | Implementation Consulting | Consultant 2 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implementation Consulting - Cyber Security Operations | Implementation Consulting | Consultant 2 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
Training & Enablement - Infrastructure Services | Training & Enablement | SME | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Training & Enablement - End User Support | Training & Enablement | SME | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Training & Enablement - Application Support | Training & Enablement | SME | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Training & Enablement - Field Communication Systems | Training & Enablement | SME | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Training & Enablement - Data Centre | Training & Enablement | SME | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Training & Enablement - SAP Support | Training & Enablement | SME | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Training & Enablement - Network Services | Training & Enablement | SME | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Training & Enablement - Cyber Security Operations | Training & Enablement | SME | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Internal Audit & Readiness - Infrastructure Services | Internal Audit & Readiness | SME | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Internal Audit & Readiness - End User Support | Internal Audit & Readiness | SME | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0
| Domestic Travel for Internal Audit- 4 Sites North | SME | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2 | 2
Internal Audit & Readiness - Application Support | Internal Audit & Readiness | SME | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0
| Domestic Travel for Implementation- 4 Sites South | SME | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 2
Internal Audit & Readiness - Field Communication Systems | Internal Audit & Readiness | SME | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Internal Audit & Readiness - Data Centre | Internal Audit & Readiness | SME | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Internal Audit & Readiness - SAP Support | Internal Audit & Readiness | SME | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
Internal Audit & Readiness - Network Services | Internal Audit & Readiness | SME | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
Internal Audit & Readiness - Cyber Security Operations | Internal Audit & Readiness | Sr Consultant | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
| Management Review | SME | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
Certification Support - Infrastructure Services | Certification Support | Consultant 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Certification Support - End User Support | Certification Support | Sr Consultant | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2
| Domestic Travel for Certification Support- 4 Sites North | Sr Consultant | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
Certification Support - Application Support | Certification Support | SME | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2
| Domestic Travel for Certification Support- 4 Sites North | SME | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
Certification Support - Field Communication Systems | Certification Support | Consultant 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Certification Support - Data Centre | Certification Support | Consultant 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Certification Support - SAP Support | Certification Support | Consultant 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Certification Support - Network Services | Certification Support | Consultant 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Certification Support - Cyber Security Operations | Certification Support | Consultant 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| Omani Trainee 1 | Trainee | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Omani Trainee 2 | Trainee | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
745
Note on AN46: Allocated to reconcile Resource Loading Total Planned PD with weekly loading for schedule and Gantt development.
Note on AO46: Allocated to reconcile Resource Loading Total Planned PD with weekly loading for schedule and Gantt development.
Note on AN47: Allocated to reconcile Resource Loading Total Planned PD with weekly loading for schedule and Gantt development.
Note on AO47: Allocated to reconcile Resource Loading Total Planned PD with weekly loading for schedule and Gantt development.
Note on AR63: Allocated to reconcile Resource Loading Total Planned PD with weekly loading for schedule and Gantt development.

## Milestone Cost Tracking
Milestone Cost Tracking - PDO ISO/IEC 20000-1 Project Plan
Milestone ID | Milestone Phase | Included Activities / Scope | Start Week | End Week | Start Date | End Date | Payment Milestone % | Planned Invoice Amount - Oman | Planned Invoice Amount - India | Invoice Status
M1 | Initiation & Governance | Initiation & Governance | 1 | 2 | 2026-09-16 | 2026-09-20 | 10% | 13578.95 | 10075.45 | Planned
M2 | Gap Assessment & Baseline Readiness | Gap Assessment | 12 | 17 | 2026-12-02 | 2027-01-10 | 30% | 40736.85 | 30226.35 | Planned
M3 | Policy & Procedure Optimization | Policy & Procedure Optimization | 18 | 25 | 2027-01-13 | 2027-03-07 | 20% | 27157.9 | 20150.9 | Planned
M4 | Implementation Support | Implementation Consulting | 16 | 40 | 2026-12-30 | 2027-06-20 | 20% | 27157.9 | 20150.9 | Planned
M5 | Internal Audit Completion | Internal Audit Completion | 27 | 38 | 2027-03-17 | 2027-06-06 | 10% | 13578.95 | 10075.45 | Planned
M6 | Certification Support & Closure | Certification Support; Domestic Travel | 39 | 40 | 2027-06-09 | 2027-06-20 | 10% | 13578.95 | 10075.45 | Planned
TOTAL | [7 empty] | 135789.5 | 100754.5
Note on A2: Source: PDO_ISO20000-1_Estimation_Draft.xlsx (Estimation and Maintenance Plan sheets) and PDO_ISO20000-1_Project Plan_ Draft_Updated.xlsx (Resource Loading sheet).

## Estimation
PDO ISO/IEC 20000-1 Estimation
Global Inputs
Project Start Date |  | Editable start date
Total Project Duration | 40 Weeks | Overall schedule- 40 Weeks
SME Rate - Oman Resource (OMR/PD) | 200 | Lead Consultant / ISO 20000 SME
Consultant Rate - Oman Resource (OMR/PD) | 125 | Implementation / documentation consultant
Omani Trainee Rate (OMR/PD) | 30 | Assumed rate for two Omani trainees
SME Rate - Indian Resource (OMR/PD) | 100 | Indian Resource
Consultant Rate - Indian Resource (OMR/PD) | 75 | Indian Resource
Travel / Logistics - Oman Resource (OMR) per Resource | 500 | Local logistics placeholder
Travel / Logistics - Indian Resource (OMR) per Resource | 3600 | Room 3000 + Travel 600 as per prior assumption
Domestic To and Fro charge through Air per Travel | 200 | Total 4 Sites. One domestic Air travel will be done and other sites will be connected through road transport.
# of Domestic Air Travels | 2 | Travel to North and South through Air and use Road Transport for reaching other 3 sites.
# of Domestic Trips | 3 | 3 Travels - 1 for implementation, 1 for Internal Audit and 1 External Audit
Total Domestic Travel Expense (Air & Road Transport) | 1200 | Domestic travel expense based on 3 travel cycles. Additive to base travel/logistics in commercial summary.
Domestic Local Road Travel Effort - 8 Sites | 8 | 8 sites x 1 PD local road travel per site = 8 PD. Effort is included in SME effort and costed separately for visibility.
Contingency % | 10% | Applied to consulting costs
Certification Body Cost Placeholder (OMR) |  | PDO Scope
Currency | OMR | Commercial currency
S.No | Service Name | Resource Input | Service Description | Gap Analysis PD | Policy & Procedure PD | Implementation PD | Training PD | Internal Audit PD | Certification Support PD | Total Service PD | Remarks
1 | Infrastructure Services | 15+ | Hosting, Database, Storage, Back-up, AD, etc. | 2 | 4 | 25 | 2 | 2 | 2 | 37 | Service effort as per given input.
2 | End User Support | 50+ | ServiceDesk & Hardware & Asset Management | 5 | 6 | 35 | 5 | 5 | 5 | 61 | Service effort as per given input.
3 | Cloud Services | Scattered across Apps Team | Cloud Hosting coordination services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Zero effort per input; included in Application Support / not separately estimated.
4 | Application Support | 50+ (incl. Contractors) | App Development, testing, run & maintain | 5 | 6 | 35 | 5 | 5 | 5 | 61 | Service effort as per given input.
5 | Field Communication Systems | 10+ | WiMAX & Tetra Services | 2 | 4 | 25 | 2 | 2 | 2 | 37 | Service effort as per given input.
6 | Data Centre | 7+ | Data Center Facilities/Infrastructure Management & Monitoring | 2 | 4 | 25 | 2 | 2 | 2 | 37 | Service effort as per given input.
7 | SAP Support | 15+ | SAP Basis & ABAP | 2 | 4 | 25 | 2 | 2 | 2 | 37 | Service effort as per given input.
8 | Network Services | 5+ | Network & Voice Collaborations | 2 | 4 | 25 | 2 | 2 | 2 | 37 | Service effort as per given input.
9 | Digital Platforms | Included in App Support | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Zero effort per input; included in Application Support / not separately estimated.
10 | Cyber Security Operations | 15+ | SOC, End-Point Sec, Threat Intell, etc. | 2 | 4 | 25 | 2 | 2 | 2 | 37 | Service effort as per given input.
|  |  |  | 22 | 36 | 220 | 22 | 22 | 22 | 344
Program Management Effort
ID | Program Management | Scope | Description | Effort PD | Resource Type
C1 | Project Initiation & Governance | All services | Kick-off, scope confirmation, governance, evidence tracker and schedule planning. | 8 | SME
C2 | Understanding of PDO Ecosystem | All services | Understand PDO organization context, IDD operating model, service landscape, stakeholder structure, technology ecosystem, supplier interfaces, service dependencies and site context before formal gap assessment. | 12 | SME
C3 | PDO Team Commitment and Availability for Gap Analysis | All services | Obtain management and team commitment for gap assessment workshops, confirm PDO SME availability, service owner participation, process owner nominations, evidence owners and workshop calendar. | 12 | SME
C4 | Mobilization and Engagement Readiness | All services | Mobilization covers onboarding, access readiness, evidence request follow-up, questionnaire clarification, detailed schedule finalization, site/audit coordination and readiness for gap analysis. | 22 | SME
C5 | Management Review Facilitation | All services | Management review preparation, facilitation, minutes and action tracking. | 4 | SME
C6 | Project Tracking | All services | Project management, governance tracking, coordination, status reporting, issue/risk follow-up and stakeholder communication. | 69 | SME
C7 | Two Omani Trainees during Implementation | Implementation phase | 2 trainees x 5 PD/week x 25 weeks for implementation assistance and knowledge transfer. | 250 | Omani Trainee
C8 | Domestic Site Travel / Local Road Travel | 8 sites | Local road travel effort for 8 sites at 1 PD per site. Supports site familiarisation, implementation coordination, internal audit readiness and certification preparation logistics. Total 3 Trips | 24 | SME / Travel
Effort Summary
Project Initiation & Governance PD |  |  | 8
Understanding of PDO Ecosystem PD |  |  | 12
PDO Team Commitment and Gap Readiness PD |  |  | 12
Mobilization & Engagement Readiness PD |  |  | 22
Service Management Lifecycle Effort PD |  |  | 344
Management Review PD |  |  | 4
Project Management Activity PD |  |  | 69
Omani Trainee Support PD |  |  | 250
Domestic Site Travel Effort PD |  |  | 24
Total Programme Effort PD |  |  | 745
Commercial Summary
Resource Model | SME Effort PD | Consultant Effort PD | Trainee Effort PD | SME Rate | Consultant Rate | Trainee Rate | Consulting Cost | Base Travel / Logistics | Domestic Travel Expense | Total Program Cost | Total Program Cost with Contigency | 6 Months Maintenance Cost | Total incl. Maintenance | Gross Margin % | Total Program Cost with GM | Total Program Cost Incl. Maintenance with GM
Using Oman Resources + Omani Trainees | 208 | 287 | 250 | 200 | 125 | 30 | 84975 | 2000 | 1200 | 88175 | 96992.5 | 17325 | 116050 | 40% | 135789.5 | 162470
Using Indian Resources + Omani Trainees | 208 | 287 | 250 | 100 | 75 | 30 | 49825 | 14400 | 1200 | 65425 | 71967.5 | 13695 | 87032 | 40% | 100754.5 | 121844.8