## Architecture
Project Governace Application
(Name to be decided)
Project Charter & Status
Measurement
(Base Measure & Metrics)
RAID & Opportunity
DE Assessment Form
Contractual Compliance
Data Integrity
Architecture
BCT Oracle Application
Other Tools Integration
( WIll be included in V2.0)
Dashboard

## Scope
Project Type | Description
Development/ Implementation/ Enhancement | Fixed-price or Time & Material software development/ enhancement projects
Support (Application/ Infrastructure) | Incident, service request, bug fixes, enhancements, SLA monitoring, Continuous IT operations, monitoring, infrastructure, SOC/NOC, helpdesk
Professional Staffing | Resource deployment, timesheets, billing, contracts, utilization
Testing | Executing test cases, tracking defects, performing regression testing, and verifying system performance, security, and usability
Cloud Maintenance | Monitoring system uptime, applying security patches, managing user access, backing up data, and optimizing infrastructure costs.
Cloud Migration | Assessing existing architecture, planning data transfers, refactoring applications for the cloud, and securely cutting over traffic.

## Dash board
Dashboard
Active Projects
Projects by Type
Delayed Projects
Open Risks
Open Issues
Pending Approvals
Project Health ( Covers 360 View of a project for Delivery Review)
Account Health
Contractual Commitment
Milestones Linked to Payment
Back

## Project Charter
Project Description |  | Progress |  | Resource Allocation <To be pulled from BCT Oracle App > |  | Treatment
Project Name | <To fill Project Name> | <Planned Start Date> | <Actual Start Date> | Resource1 | 1 FTE | Applicable Phase | <Reqm/ Design/ CUT/ Build & Deployment/ Testing/UAT/Warranty/ Support> | <Description>
Project ID | <Auto Generated> | <Planned End Date> | <Actual End Date> | Resource2 | 0.5 FTE | Delivery Declared Project Health | Overall Auto Calculated, even if one parameter is red, the overall rating shall be red. Core Delivery - <Red/ Potential Red/ Amber/ Green> (Scope/ Cost/ Scheule/ Quality/ Contractual SLA/ KPI) People - <Red/ Potential Red/ Amber/ Green> (Resourcing/ Fulfilment/ Skilling/ Performance/ Attrition) Operational - <Red/ Potential Red/ Amber/ Green> (PID Creation/ Extension/ Contract Extension/PO/ Projects without contract/ Payment / Invoices/ Timesheet) Customer - <Red/ Potential Red/ Amber/ Green> (Relation/ Pulse/ Feedback/ Opportunities/ Business) Financial - <Red/ Potential Red/ Amber/ Green> - (Forecast/ Margin/ MIP) Compliance - - <Red/ Potential Red/ Amber/ Green> - (Security/ Infrastructure/ Vendor Management) | <Delivery Description>
Contract Type | FPP/ TM/ Capped TM/ Internal <Data to be updated from PMO Input> | <Planned Duration> | <Actual Duration> | Resource3 | 0.25 FTE | Delivery Declared Overall Project Health | <Red/ Potential Red/ Amber/ Green> - Auto Calculated
Project Type | <Development/ Maintenance/ Professional Staffing/Support (Application/ Infrastructure)/ Testing/ Cloud Maintenance/ Cloud Migration> |  |  | Resource4 | 1 FTE | DE Assessed Project Health | <Red/ Potential Red/ Amber/ Green> - Static <Pulled form DE Assessment Sheet> | <DE Description>
Organization | BCTPL/BCTC/ FT <Data to be updated from PMO Input> |  |  | Resource5 | 1 FTE | Project Status | <Start Up/ Execution/ Hold/ Closed/ Open Only for Billing> | <Description>
Project Owned | Fully Owned/Co-Owned/ Customer Driven |  |  | Resource6 | 1 FTE | Overall Project Health | <Red/ Potential Red/ Amber/ Green> | Infered from highest status
GEO | <APAC/ MEA/ US> <Data to be updated from PMO Input> |  |  | Resource7 | 1 FTE
Account Name | <To fill Account Name> |  |  | Resource8 | 1 FTE
Project Manager | <Name of the PM> |  |  | Resource9 | 1 FTE
Delivery Manager | <Name of the Delivery Manager>
Delivery Excellence | <Name of the Delivery Excellence> |  |  | Head Count | <Auto Calculated from Resource>
Customer Overview | < Describe Customer Business and landscape> |  |  | FTE | <Auto Calculated from Resource>
Project Scope Description | <Project Scope & Short Description>
Project Revenue
Project Currency
Oracle Project IDs
FPP/ FB/ T&M/Product/ Unit Based Billing/ Others
Implementation/ Support/

## Project Status
Project Status
Project Current Status | Description
Key Accomplishments | <Provide the accomplishments from last report to now, including client appreciations in the form of bullets>
UPCOMING KEY RELEASES/ MILESTONES/ ACTIONS | <Provide Upcoming key activities to focus in the form of bullets>
LEADERSHIP SUPPORT/ ATTENTION REQUIRED | <Provide the areas where leadership support is required – in the form of bullets>

## Measurement
Development Projects
Measure | Catergory |  |  | Unit of Measure | Metrics |  | Unit | Mandatory
| High | Medium | Low
Oveall Planned Size | NA | NA | NA | CP/ FP/ LOC/ Other | Productivity |  | Size/ Person-Day | Y
Actual Size (End od the Project) | NA | NA | NA | CP/ FP/ LOC/ Other | Effort Variation | % | % | Y
Overall Estimated Effort | NA | NA | NA | Person-Hourss | Schedule Performance Index (SPI) | No Unit | No Unit | Y
Planned Effort (As on Date) | NA | NA | NA | Person-Hourss | Cost Performance Index (CPI) | No Unit | No Unit | Y
Actual Effort (As on Date) | NA | NA | NA | Person-Hourss | Defect Leakage(Internal Vs External) |  | % | Y
Planned % of Completion (As on Date) | NA | NA | NA | % | Code Coverage ( Tool Based ) |  | % | N
Actual % of Completion (As on Date) | NA | NA | NA | % | Test Execution Coverage (%) |  | % | Y
URD Defects - Internal |  |  |  | Count | Test Pass Rate (%) |  | % | Y
URD Defects - External |  |  |  | Count
Proto Defects - Internal |  |  |  | Count
Proto Defects - External |  |  |  | Count
SRS Defects - Internal |  |  |  | Count
SRS Defects - External |  |  |  | Count
ADD Defects - Internal |  |  |  | Count
ADD Defects - External |  |  |  | Count
HLD Defects - Internal |  |  |  | Count
HLD Defects - External |  |  |  | Count
USP/ LLD Defects - Internal |  |  |  | Count
USP/ LLD Defects - External |  |  |  | Count
Code Defects - Internal |  |  |  | Count
Code Defects - External |  |  |  | Count
UTC Defects - Internal |  |  |  | Count
UTC Defects - External |  |  |  | Count
SITC Defects - Internal |  |  |  | Count
SITC Defects - External |  |  |  | Count
UT Defects - Internal |  |  |  | Count
UT Defects - External |  |  |  | Count
SIT Defects - Internal |  |  |  | Count
SIT Defects - External |  |  |  | Count
UAT Defects - External |  |  |  | Count
Production Defects - External |  |  |  | Count
Total Number of Test Cases Designed |  |  |  | Count
# of Executed Test Cases | NA | NA | NA | Count
# of Passed Test Case | NA | NA | NA | Count
Last Updated Date < Default Date to be Displayed> | NA | NA | NA
Support ( Application/ Infrastructure)
Measurement |  |  |  |  | Metrics |  | Unit
Ticket Type | Catergory | Unit of Measure |  |  | Incident (P1/P2/P3) - SLA Compliance % |  | %
Incidents | P1 | Count | Person-days |  | Incident (P1/P2/P3) - MTTR |  | Person-Hours/ # of Incidents
| P2 | Count | Person-days |  | Service Request - MTTR |  | Person-Hours/ # of SR
| P3 | Count | Person-days |  | User Clarification- MTTR |  | Person-Hours/ # of UC
Service Request | NA | Count | Person-days
User Clarification | NA | Count | Person-days
# of Ticket Re-Opened | NA | Count
# Of Aging Tickets | NA | Count
# Of First Time Resolution | NA | Count
Professional Staffing
Measure |  | Units |  |  | Metrics |  | Units
No of request | NA | Count |  |  | Average Response Time to a request for resources | Critical (P1) | Person-Hours/ # of Resource Request
Response Time to a request for resources | Critical (P1) | Person-Hours |  |  |  | High (P2) | Person-Hours/ # of Resource Request
| High (P2) | Person-Hours |  |  |  | Medium (P3) | Person-Hours/ # of Resource Request
| Medium (P3) | Person-Hours |  |  |  | Low (P4) | Person-Hours/ # of Resource Request
| Low (P4) | Person-Hours |  |  | Percentage of profiles that Qualify for Client Submissions (Profile submission vs Client Interview ) |  | %
# of Profiles Submitted | NA | Count |  |  | Percentage of candidates that result in Joining (Interview Selects v Joined) |  | %
# of Client Interviews | NA | Count |  |  | Lead Time - Resource Request to Onboarding | Critical (P1) | Person-Days/ # of Onboarding
# of Interview Selects | NA | Count |  |  |  | High (P2) | Person-Days/ # of Onboarding
# of Associates Joined | NA | Count |  |  |  | Medium (P3) | Person-Days/ # of Onboarding
Lead Time - Resource Request to Onboarding | Critical (P1) | Person-Days |  |  |  | Low (P4) | Person-Days/ # of Onboarding
| High (P2) | Person-Days
| Medium (P3) | Person-Days
| Low (P4) | Person-Days
Testing
Measurements | Unit |  |  |  | Metric |  | Unit
Total Number of Test Cases Designed | Count |  |  |  | Test Execution Coverage (%) |  | %
# of Executed Test Cases | Count |  |  |  | Test Pass Rate (%) |  | %
# of Passed Test Case | Count |  |  |  | Automation Coverage (%) |  | %
# of Test Case Automated | Count |  |  |  | Test Design Productivity |  | # of Test Case Designed/ Person-Days
Effort Spent for Test Case Design | Person-Days |  |  |  | Test Execution Productivity |  | # of Executed Test Cases/ Person-Days
Effort Spent for Test Execution | Person-Days
Cloud Maintenance Project
Measurements | Unit |  |  |  | Metrics |  | Unit
Total Uptime | Person-Days |  |  |  | Service Availability (%) |  | %
Total Scheduled Time | Person-Days |  |  |  | Application Availability (%) |  | %
Application Downtime | Person-Days
Cloud Migration Projects
Measurements | Units |  |  |  | Metrics |  | Unit
Planned Application Migration | Count |  |  |  | Applications Migrated ( Planned Vs Actual) |  | %
Applications Migrated | Count |  |  |  | Migration Success Rate ( Success Vs Total) |  | %
Total Migration Attempts | Count |  |  |  | Migration Downtime |  | Person-Hours
Successful Migrations | Count
Migration End Time | Date and Time
Migration Start Time | Date and Time

## Contractual Compliance
Contractual Commitment Definition
Frequency | Name of the Commitment | Formula | Target | Penalty Applicable | Penalty Value
One Time/Weekly/ Fortnight/ Monthly/ Quaterly/ Half Yearly/ Phase Wise |  |  |  | Yes/ No
Contractual Commitment Actual
Frequency | Name of the Commitment | Formula | Target | Penalty Applicable | Penalty Value | Actual | Met/ Not Met
Static | Static | Static | Static | Static | Static
Milestones Linked to Payment Definition
Milestone Name | Milestone Description | Expected Date of Payment | Expected Payment Value
Milestones Linked to Payment Actual
Milestone Name | Milestone Description | Expected Date of Payment | Expected Payment Value | Actual Date of Payment | Actual Payment Value | Status | Remarks
Static | Static | Static | Static |  |  | Paid On Time/ Delayed Payment/ Yet To Be Paid

## Risk
Field | Description
Risk ID | Unique identifier | Auto Generated
Project Name | Related project | Default
Project Type | <Development/ Maintenance/ Professional Staffing/Support (Application/ Infrastructure)/ Testing/ Cloud Maintenance/ Cloud Migration> | Default
Risk Title | Short description
Risk Description | Detailed explanation
Risk Category | Core Delivery / People /Operational / Customer / Financial / Compliance
Risk Type | Internal / External
Identified By | Person identifying the risk
Identified Date | Date recorded
Risk Owner | Responsible person
Trigger/Event | Event indicating the risk may occur
Probability | Very Low, Low, Medium, High, Very High
Impact | Very Low, Low, Medium, High, Critical
Risk Score | Probability × Impact
Severity | Low, Medium, High, Critical
Affected Deliverables | Deliverables at risk
Affected Milestone | Related milestone
Response Strategy | Avoid, Mitigate, Transfer, Accept
Mitigation Plan | Preventive actions
Contingency Plan | Actions if the risk occurs
Residual Risk | Remaining risk after mitigation
Target Resolution Date | Planned completion
Current Status | Open, Monitoring, Closed
Escalation Required | Yes / No
Escalated To | Higher authority
Last Review Date | Latest review
Next Review Date | Planned review
Closure Date | Date closed
Remarks | Notes

## Opportunity
Field | Description
Opportunity ID | Unique identifier
Project Name | Related project
Project Type | <Development/ Maintenance/ Professional Staffing/Support (Application/ Infrastructure)/ Testing/ Cloud Maintenance/ Cloud Migration>
Opportunity Title | Short description
Opportunity Description | Detailed explanation
Category | Core Delivery / People /Operational / Customer / Financial / Compliance
Identified By | Person identifying the opportunity
Identified Date | Date recorded
Opportunity Owner | Responsible person
Impact | Very Low, Low, Medium, High
Expected Benefit | Time, Cost, Quality, Revenue
Estimated Benefit | Quantified value
Benefit Type | Cost Saving, Revenue Increase, Quality Improvement, Customer Satisfaction
Exploitation Strategy | Exploit, Enhance, Share, Accept
Action Plan | Planned actions
Target Implementation Date | Planned completion
Status | Identified, Approved, Implemented, Closed
Approval Required | Yes / No
Approved By | Approver
Actual Benefit | Realized outcome
Closure Date | Date completed
Remarks | Notes

## Dependencies
Field | Description
Dependency ID | Unique identifier
Project Name | Related project
Project Type | <Development/ Maintenance/ Professional Staffing/Support (Application/ Infrastructure)/ Testing/ Cloud Maintenance/ Cloud Migration>
Dependency Title | Short description
Description | Detailed dependency
Dependency Type | Internal, External, Vendor, Customer, Infrastructure, Regulatory, Third Party
Category | Core Delivery / People /Operational / Customer / Financial / Compliance
Depends On | Team, task, project, vendor, or customer
Related Task/Milestone | Linked project activity
Required By | Needed before this date
Owner | Responsible person
Dependency Status | Not Started, In Progress, Completed, Blocked
Criticality | Low, Medium, High, Critical
Impact if Delayed | Expected consequence
Probability of Delay | Low, Medium, High
Mitigation Plan | Risk reduction action
Escalation Required | Yes/No
Escalation Level | Project Manager, Delivery Manager, Steering Committee
Actual Completion Date | When dependency was completed
Last Updated | Last modification date
Remarks | Additional comments

## Issues
Field | Description
Issue ID | Unique identifier
Project Name | Related project
Project Type | <Development/ Maintenance/ Professional Staffing/Support (Application/ Infrastructure)/ Testing/ Cloud Maintenance/ Cloud Migration>
Issue Title | Short description
Issue Description | Detailed explanation
Issue Category | Core Delivery / People /Operational / Customer / Financial / Compliance
Priority | Low, Medium, High, Critical
Severity | Minor, Major, Critical
Raised By | Person reporting the issue
Raised Date | Date reported
Assigned To | Responsible person
Root Cause | Underlying cause
Business Impact | Effect on project
Affected Deliverables | Deliverables impacted
Affected Milestone | Related milestone
Resolution Plan | Planned solution
Due Date | Target resolution date
Actual Resolution Date | Completion date
Status | New, Assigned, In Progress, Pending, Resolved, Closed
Escalation Level | PM, Delivery Manager, Steering Committee
Escalation Date | Date escalated
Resolution Summary | Final resolution
Lessons Learned | Preventive improvements
Closure Date | Date closed
Remarks | Notes

## Assumption
Field | Description
Assumption ID | Unique identifier
Project Name | Related project
Project Type | <Development/ Maintenance/ Professional Staffing/Support (Application/ Infrastructure)/ Testing/ Cloud Maintenance/ Cloud Migration>
Title | Short description
Detailed Description | Full assumption statement
Category | Core Delivery / People /Operational / Customer / Financial / Compliance
Raised By | Person who recorded the assumption
Raised Date | Date created
Owner | Responsible person
Dependency Reference | Linked dependency (optional)
Impact if Invalid | Consequences if assumption fails
Probability of Failure | Low / Medium / High
Impact Rating | Low / Medium / High / Critical
Validation Date | Planned review date
Validation Status | Pending, Validated, Invalid
Mitigation Plan | Action if assumption proves false
Contingency Plan | Backup plan
Current Status | Open, Closed, Cancelled
Last Updated | Last modification date
Remarks | Additional comments

## DE Assessment Form
DE Assessment Form
DE Assessed Project Health | <Red/ Potential Red/ Amber/ Green> | if not green | Alert ID
Alert Category <Core Delivery / People /Operational / Customer / Financial / Compliance>
Alert Brief description
Detailed Description
Raised By
Raised On
PCI Score
Key Findings | 1 | Classification<Observation/ Recommendation> | Action Taken | Date | Status (Open/ Closed/ On Hold/ Deferred) | Remarks (if Any)
2
3

## Data Integrity
Data | Status
Planned Size | Updated/ Not Updated
Actual Size | Updated/ Not Updated
Planned Effort | Updated/ Not Updated
Actual Effort | Updated/ Not Updated
Planned % of Completion | Updated/ Not Updated
Actual % of Completion | Updated/ Not Updated
URD Defects - Internal | Updated/ Not Updated
URD Defects - External | Updated/ Not Updated
Proto Defects - Internal | Updated/ Not Updated
Proto Defects - External | Updated/ Not Updated
SRS Defects - Internal | Updated/ Not Updated
SRS Defects - External | Updated/ Not Updated
ADD Defects - Internal | Updated/ Not Updated
ADD Defects - External | Updated/ Not Updated
HLD Defects - Internal | Updated/ Not Updated
HLD Defects - External | Updated/ Not Updated
USP/ LLD Defects - Internal | Updated/ Not Updated
USP/ LLD Defects - External | Updated/ Not Updated
Code Defects - Internal | Updated/ Not Updated
Code Defects - External | Updated/ Not Updated
UTC Defects - Internal | Updated/ Not Updated
UTC Defects - External | Updated/ Not Updated
SITC Defects - Internal | Updated/ Not Updated
SITC Defects - External | Updated/ Not Updated
UT Defects - Internal | Updated/ Not Updated
UT Defects - External | Updated/ Not Updated
SIT Defects - Internal | Updated/ Not Updated
SIT Defects - External | Updated/ Not Updated
UAT Defects - External | Updated/ Not Updated
Production Defects - External | Updated/ Not Updated
Total Number of Test Cases Designed | Updated/ Not Updated
# of Executed Test Cases | Updated/ Not Updated
# of Passed Test Case | Updated/ Not Updated
Incidents details | Updated/ Not Updated
Service Request details | Updated/ Not Updated
User Clarification details | Updated/ Not Updated
# of Ticket Re-Opened | Updated/ Not Updated
# Of Aging Tickets | Updated/ Not Updated
# Of First Time Resolution | Updated/ Not Updated
No of request | Updated/ Not Updated
Response Time to a request for resources | Updated/ Not Updated
# of Profiles Submitted | Updated/ Not Updated
# of Client Interviews | Updated/ Not Updated
# of Interview Selects | Updated/ Not Updated
# of Associates Joined | Updated/ Not Updated
Lead Time - Resource Request to Onboarding | Updated/ Not Updated
Total Number of Test Cases Designed | Updated/ Not Updated
# of Executed Test Cases | Updated/ Not Updated
# of Passed Test Case | Updated/ Not Updated
# of Test Case Automated | Updated/ Not Updated
Effort Spent for Test Case Design | Updated/ Not Updated
Effort Spent for Test Execution | Updated/ Not Updated
Total Uptime | Updated/ Not Updated
Total Scheduled Time | Updated/ Not Updated
Application Downtime | Updated/ Not Updated
Planned Application Migration | Updated/ Not Updated
Applications Migrated | Updated/ Not Updated
Total Migration Attempts | Updated/ Not Updated
Successful Migrations | Updated/ Not Updated
Migration End Time | Updated/ Not Updated
Migration Start Time | Updated/ Not Updated
Risk | Updated/ Not Updated
Assumption | Updated/ Not Updated
Opportunity | Updated/ Not Updated
Dependencies | Updated/ Not Updated
Issues | Updated/ Not Updated
Delivery Declared Project Health | Updated/ Not Updated
DE Assessed Project Health | Updated/ Not Updated
Project Status | Updated/ Not Updated
Contractual Commitment Definition | Updated/ Not Updated
Contractual Commitment Actual | Updated/ Not Updated
Milestones Linked to Payment Definition | Updated/ Not Updated
Milestones Linked to Payment Actual | Updated/ Not Updated

## Integration
Integrate with:
Microsoft 365
BCT Oracle Application
Ticketing Tools
Existing Project Management tools

## Security
Features:
Role-Based Access Control (RBAC)
Multi-Factor Authentication (MFA)
Audit Trail
Activity Logs
Data Encryption
Backup and Restore

## Login
Login Screen
Access for the following roles
Admin
CEO/ CDO/ GEO Head/ Delivery Manager
Project Manager
| User Name : | Project Team Member
| Password : | Delivery Excellence
PMO
LDAP to be Implemented
Login

## Action
SNO | Actions | Status
1 | Clean Up the Sheets | Completed
2 | Architecture | Completed
3 | Name the Tool (Not Project Management, more from project governance) | Yet To Start
4 | Discuss with Hariharasudhan | Yet To Start
5 | Discuss with Geo Heads | Yet To Start
6 | Discuss with Vivek | Yet To Start
7 | Discuss with Sowmya/ Revathi | Yet To Start